## Leveling
439 Manning Ave: Base Scope Bid Leveling vs Budget and 35% Markup Target
Scenario: Fabiano at $20,000 incl. demo ¦ Roof/siding: Safety
Division | Budget (cost) | Lowest approved bid | Low bidder | Current: Renomar | Scenario: Fabiano | Scenario vs budget | # prices in | # required (SOP)
General Works (bulk) | 30041 | 57100 | Renomar Inc (Olimpiu) | 57100 | 20000 | -10041 | 1 | 4
Demolition (separate line) | 6290 | 0 | No price yet | 0 | 0 | -6290 | 0 | 3
Framing & Structure | 23128 | 14000 | Aryan | 14000 | 14000 | -9128 | 1 | 3
Lumber Supply | 4900 | 6386.19 | RONA (Jonathan) | 6386.19 | 6386.19 | 1486.19 | 3 | 3
Flat Roofing | 8010 | 15700 | Alps Roofing | 0 | 0 | 0 | 1 | 3
Siding / Cladding | 17750 | 7900 | Baz Aluminum | 0 | 0 | 0 | 1 | 3
Roof + Siding Combo (Safety) | 0 | 20580 | Safety Roofing (Elvis) | 20580 | 20580 | -5180 | 1 | 1
HVAC: Mini-Split | 6750 | 9370 | Ideal Heating (Leena) | 9370 | 9370 | 2620 | 2 | 3
Spray Foam | 3430 | 3360.5 | FoamIt (Nadia) | 3360.5 | 3360.5 | -69.5 | 1 | 3
Site Services & Hoisting | 11500 | 0 | No price yet: budget carried | 11500 | 11500 | 0 | 0 | 1
BASE COST TOTAL | 111799 |  |  | 122296.69 | 85196.69 | -26602.31
MARGIN CHECK |  |  |  | Current: Renomar | Scenario: Fabiano
Contract sell (pre-HST) |  |  |  | 114070 | 114070
Cost target = sell / (1 + markup) |  |  |  | 84496.2963 | 84496.2963
Base cost (from total above) |  |  |  | 122296.69 | 85196.69
Over / (under) cost target |  |  |  | 37800.3937 | 700.3937
Gross profit |  |  |  | -8226.69 | 28873.31
Margin (profit / sell) |  |  |  | -7.212% | 25.31%
Markup (profit / cost) |  |  |  | -6.727% | 33.89%
Target margin at that markup |  |  |  | 25.93% | 25.93%
RISK VIEW: + contingency + provisional
Contingency |  |  |  | 12229.669 | 8519.669
Provisional: structural reinforcement |  |  |  | 5000 | 5000
All-in cost |  |  |  | 139526.359 | 98716.359
All-in profit |  |  |  | -25456.359 | 15353.641
All-in margin |  |  |  | -22.32% | 13.46%
ADD-ONS: bid vs what the client was told
Add-on | Budget (cost) | Lowest bid | Low bidder | Client was told (sell) | Sell at 35% markup | Gap: needed sell - told
Brick Veneer (exterior) | 36400 | 31200 | Amoroso Construction | 8000 | 42120 | 34120
Rustic Interior Brick Wall | 3960 | 10800 | Amoroso Construction | 3600 | 14580 | 10980
Angled Skylight | 4600 | 3300 | Skylight Services Ltd | 2500 | 4455 | 1955
Windows: CLIENT-PAID, NOT IN BASE COST (info only) | 8470 | 7850 | JS Windows and Doors
Finish materials: CLIENT-PAID, NOT IN BASE COST (hardwood, interior doors, hardware) | 7549 |  | Tender Package P9 budget; client selections
Notes
Amounts come from the cost field on each JobTread bid request. Quote PDFs not reviewed, so scope inclusions and HST treatment are unconfirmed.
Contract sell $114,070 is the 2.0 Rear Addition base only (excludes design fees and add-ons), per the Tender Package margin check.
Base cost EXCLUDES windows (supply + install) and all client finish materials (hardwood, interior doors, hardware). Base includes only the install labour for hardwood, doors and trim inside General Works.
Confirm Renomar's and Fabiano's prices do NOT include supply of hardwood, interior doors or hardware, or window install. If they do, deduct it.
Safety Roofing combo includes the skylight (an add-on), so the base is slightly overstated when Safety is selected. That's conservative.
Site Services has no quote yet; the $11,500 budget is carried at cost.
Confirm with Fabiano: demo as a separate line, licensed electrician + ESA included, and materials (drywall, insulation, trim) included.
Note on A6: Renomar's $57,100 covers General Works + Demo, so demo is $0 in the Current column. In the Fabiano scenario, demo is $0 if Inputs says his price includes it; otherwise the demo cost from Inputs is added.
Note on A14: No quote yet. Budget is carried at cost in both columns until rental quotes come in.
Note on A21: Positive = over the cost target (bad). Zero or negative = within tolerance.
Note on A36: Budget is the net brick delta over vinyl ($48,750 brick less $12,350 vinyl credit). Client told about $8,000.
Note on A37: Client quoted about $3,600 sell.
Note on A38: Client told $2K to $3K incl. labour; midpoint used. Aluplex $300 excluded as a partial price (see All Bids).
Note on B40: Client budget for windows. Supply AND install are excluded from the contract (General Note 3). Window bids are tendered only so the client can order and we can lock the schedule.
Note on E5: Renomar's approved bid covers General Works + Demo combined.
Note on G11: When Safety is selected, the combo is compared against the Flat Roofing + Siding budgets combined ($25,760), and those two rows show no variance. The combo also includes the skylight.

## Inputs
439 Manning Ave: Bid Leveling Inputs
Yellow cells are the levers. Change them and every tab updates. Blue = typed-in number, black = formula, green = pulled from another tab.
Input | Value | Source / note
Contract sell: 2.0 Rear Addition (pre-HST) | 114070 | Tender Package, Margin Check (from invoice #22288). Excludes design fees and add-ons.
Target markup on cost (SOP Step 5) | 35% | Tendering SOP: cost target = contract sell / 1.35.
Fabiano General Works price (estimate) | 20000 | Raff's estimate, Oct 20. Replace with the real number when it comes in.
Does Fabiano's price include demolition? (Yes/No) | Yes | The work order asks for demo as a separate line. If No, the demo cost below gets added.
Demolition cost if separate | 6290 | Internal demo budget (P7D). Replace with Fabiano's or Doctor Demo's price.
Roof + siding option (Split / Safety) | Safety | Split = Alps roof + Baz siding. Safety = Safety Roofing combo (siding, flat roof and skylight).
Construction contingency (% of cost) | 10% | Tender Package: 10% budget reserve.
Provisional: structural reinforcement | 5000 | Tender Package P2 provisional / change order risk.

## All Bids
All Manning Bid Requests (from JobTread, Oct 20, 2026)
Amounts are the cost entered on each JobTread bid request. HST treatment not confirmed. To add a bid, insert a row above the last one and copy column E down.
Division | Vendor | Status | Amount ($) | Lookup key (formula) | JobTread #
General Works + Demo | Renomar Inc (Olimpiu) | Approved | 57100 | General Works + Demo¦57100 | 46
General Works + Demo | FV Renovations (Fabiano) | Pending | 0 |  | 15
Demolition | Doctor Demo (Roman) | Pending | 0 |  | 10
Demolition | Bradley Demolition | Declined | 0 |  | 41
Demolition | Universal Impact Services | Declined | 0 |  | 42
Framing | Aryan | Approved | 14000 | Framing¦14000 | 31
Framing | New Age Construction (Mario) | Pending | 0 |  | 17
Framing | Bogdan | Declined | 0 |  | 30
Lumber | RONA (Jonathan) | Approved | 6386.19 | Lumber¦6386.19 | 43
Lumber | Central Fairbank (Bruno) | Approved | 7040 | Lumber¦7040 | 50
Lumber | KOTT (Jon Stark) | Approved | 7208.9 | Lumber¦7208.9 | 45
Flat Roofing | Alps Roofing | Approved | 15700 | Flat Roofing¦15700 | 21
Flat Roofing | CA Roofing (Jason) | Declined | 0 |  | 32
Flat Roofing | Ebi | Declined | 0 |  | 33
Siding | Baz Aluminum | Approved | 7900 | Siding¦7900 | 38
Siding | SM Cladding (Milos) | Declined | 0 |  | 39
Roof + Siding + Skylight Combo | Safety Roofing (Elvis) | Approved | 20580 | Roof + Siding + Skylight Combo¦20580 | 49
HVAC | Ideal Heating (Leena) | Approved | 9370 | HVAC¦9370 | 28
HVAC | MiTech HVAC (Mikel) | Approved | 9950 | HVAC¦9950 | 18
HVAC | Sentral HVAC | Declined | 0 |  | 27
HVAC | MMS HVAC | Declined | 0 |  | 29
Spray Foam | FoamIt (Nadia) | Approved | 3360.5 | Spray Foam¦3360.5 | 13
Windows (client-paid) | JS Windows and Doors | Approved | 7850 | Windows (client-paid)¦7850 | 16
Windows (client-paid) | Kingshore Windows | Approved | 8340 | Windows (client-paid)¦8340 | 47
Windows (client-paid) | WELDA Windows & Doors | Approved | 9646.02 | Windows (client-paid)¦9646.02 | 37
Add-on: Brick Veneer | Amoroso Construction | Approved | 31200 | Add-on: Brick Veneer¦31200 | 12
Add-on: Interior Brick | Amoroso Construction | Approved | 10800 | Add-on: Interior Brick¦10800 | 14
Add-on: Skylight | Skylight Services Ltd | Approved | 3300 | Add-on: Skylight¦3300 | 24
Add-on: Skylight | Aluplex | Approved (partial) | 300 |  | 26
Hardwood Install (in GW scope) | Reno Factory (Roland) | Approved | 1215 | Hardwood Install (in GW scope)¦1215 | 22
Note on C33: Marked Approved in JobTread, but $300 looks like a partial price (unit only?). Excluded from the low-bid lookup. Change the status to Approved to include it.