## Summary
38 Harewood Ave: Bid Leveling Summary
Julianne & David Lee · Second-floor addition + bathroom + front porch + main-floor beam/posts · INTERNAL, DO NOT SEND · Blue = input · Prepared Oct 21, 2026
INPUTS
Input | Value |  | Source / note
Target margin (profit ÷ selling price) | 40% |  | Per Raff: 40%. Matches JobTread budget convention (price = cost ÷ 0.60).
Construction duration (weeks) | 24 |  | Per Raff: ~6 months. Drives PM, site labour and overhead lines.
Option A contract price (pre-HST) | 271379.75 |  | Joist 110-351 Rev 1 (Sep 18, 2026): Section 2.0 $269,754.25 + service fee $1,625.50.
Beam & posts price (pre-HST) | 16500 |  | Recommended price, not yet sent to client (promised after Oct 16 visit).
HST rate | 13% |  | Ontario HST.
COST ROLL-UP (from Bid Leveling tab)
Line | Internal-rate cost | Carried cost | Note
General requirements & site | 100700 | 100700
Porch | 6692 | 6692
Structure (lumber + framing) | 29106 | 29349.01
Exterior envelope | 56400 | 56045
Mechanical & electrical | 19600 | 17237
General trades bulk scope (FV) | 53550.9 | 37500
Finishes & stairs | 15250 | 16670
Main-floor beam & posts | 8200 | 8200
TOTAL COST (all-in: trades, materials, PM, site labour, overhead) | 289498.9 | 272393.01 | Carried = selected bid, or internal unit rate where no bid was received.
of which time-based (PM + site labour + overhead) | 79200 | 79200
Hard costs only (excl. time-based) | 210298.9 | 193193.01
PRICING CHECK vs 40% TARGET
Line | Amount | Margin | Note
Current contract price (Option A + beam, pre-HST) | 287879.75 |  | What the Lees have been quoted (beam not yet sent).
Net profit at current price (all-in carried cost) | 15486.74 | 5.38% | Margin column = profit ÷ price.
Price needed for target margin, all-in cost | 453988.35 | 40% | Cost ÷ (1 − margin). PM, labour and overhead included.
Gap vs current price | 166108.6 |  | Positive = price needs to go up by this much.
Price at 40% MARKUP on all-in cost (cost × 1.40) | 381350.214 | 28.57% | If '40% on top of cost' means markup, this is the price (28.6% margin).
Gap vs current price (markup method) | 93470.464
Price needed for target margin, hard costs only | 321988.35 | 40% | JobTread-style: 40% margin on trade/material cost; PM/OH absorbed inside the margin.
Gap vs current price (hard-cost method) | 34108.6
Margin left after PM/labour/OH at hard-cost price | 49595.34 | 15.4% | What 40% on hard cost actually nets once time-based costs come out.
Low-bid scenario: total carried if every bid line takes the lowest bid | 263612.35 | 8.43% | Margin column = margin at current price using all low bids.

## Bid Leveling
38 Harewood Ave: Bid Leveling Sheet
Project Address: 38 Harewood Ave, Scarborough, ON M1M 2R2 · Client: Julianne & David Lee · Floor area (2nd-floor addition): ~693 sq ft + porch ~85 sq ft
Carried cost = Override (blue) if entered, else lowest bid received, else internal rate × qty. Bids = JobTread job #6 bid requests. Internal rates = 38 Harewood INTERNAL ESTIMATE / PalmView Cost Index (Manning tender package). PalmView Final Cost = carried ÷ (1 − target margin).
# | Description (Scope) | Internal PalmView Unit Rate | Total Units | Unit of Measure | Cost based on internal rates | % of project (carried) | PalmView Final Cost (sell) | Take Rate (profit $) | Carried Subtrade Cost | Basis | Override (carry this) | Lowest bid | Bidder 1 (Name) | Bidder 1 Quote | Bidder 2 (Name) | Bidder 2 Quote | Bidder 3 (Name) | Bidder 3 Quote | Bidder 4 (Name) | Bidder 4 Quote | Notes / scope gaps | Low-bid scenario cost | Carried vs internal (+ = over)
GENERAL REQUIREMENTS & SITE
1 | Temporary hoarding & safety fences | 3000 | 1 | Lump Sum | 3000 | 1.101% | 5000 | 2000 | 3000 | Internal rate | [10 empty] | Internal estimate. | 3000 | 0
2 | Temporary toilet & temporary hydro | 3500 | 1 | Lump Sum | 3500 | 1.285% | 5833.3333 | 2333.3333 | 3500 | Internal rate | [10 empty] | Internal estimate. Index: toilet $250/mo. | 3500 | 0
3 | Misc. supplies, materials & garbage | 2000 | 1 | Lump Sum | 2000 | 0.7342% | 3333.3333 | 1333.3333 | 2000 | Internal rate | [10 empty] | FV bid includes the disposal bin. | 2000 | 0
4 | Safety supplies & 3rd-party inspections | 2500 | 1 | Lump Sum | 2500 | 0.9178% | 4166.6667 | 1666.6667 | 2500 | Internal rate | [10 empty] | Internal estimate. | 2500 | 0
5 | Scaffold rental (2nd-floor exterior) | 1500 | 2 | Months | 3000 | 1.101% | 5000 | 2000 | 3000 | Internal rate | [10 empty] | Cost Index rate (Manning). No quote yet: get rental quote. | 3000 | 0
6 | Weather protection while roof is off (tarps, temp roof) | 1500 | 1 | Lump Sum | 1500 | 0.5507% | 2500 | 1000 | 1500 | Internal rate | [10 empty] | Manning used $1,200 for a smaller roof. | 1500 | 0
7 | Engineer field reviews (piers, framing per S1.01) | 1500 | 1 | Lump Sum | 1500 | 0.5507% | 2500 | 1000 | 1500 | Internal rate | [10 empty] | Allowance. | 1500 | 0
8 | Final clean, deficiencies, final inspections | 4500 | 1 | Lump Sum | 4500 | 1.652% | 7500 | 3000 | 4500 | Internal rate | [10 empty] | Internal estimate (scaled). | 4500 | 0
9 | Site supervision & project manager | 1700 | 24 | Weeks | 40800 | 14.98% | 68000 | 27200 | 40800 | Internal rate | [10 empty] | Sean's budget rate × duration (Summary). | 40800 | 0
10 | Site labour | 600 | 24 | Weeks | 14400 | 5.286% | 24000 | 9600 | 14400 | Internal rate | [10 empty] | Sean's budget rate × duration. | 14400 | 0
11 | Company overhead (insurance, WSIB, office, vehicles) | 1000 | 24 | Weeks | 24000 | 8.811% | 40000 | 16000 | 24000 | Internal rate | [10 empty] | Per Raff: ~$1,000/week. | 24000 | 0
| SUBTOTAL: GENERAL REQUIREMENTS & SITE |  |  |  | 100700 | 36.97% | 167833.3333 | 67133.3333 | 100700
FRONT COVERED PORCH
12 | Concrete piers, 10" dia, min. 48" below grade (F1) | 500 | 4 | Each | 2000 | 0.7342% | 3333.3333 | 1333.3333 | 2000 | Internal rate |  |  | MBS Contracting (pending) |  | Windmill Group (pending) |  | Msix Contractors (pending) |  |  |  | All 3 bids still pending in JobTread. Raff's number $2,000. Drawings show 3 piers; bid scope says 4: confirm. | 2000 | 0
13 | PT framing, decking & railing material (~85 SF deck, 30 LF rail) | 41.2 | 85 | Square Foot | 3502 | 1.286% | 5836.6667 | 2334.6667 | 3502 | Internal rate | [10 empty] | Framer bids are labour only. Allowance ≈ $3,500. | 3502 | 0
14 | T&G porch ceiling (1x6 pine) | 14 | 85 | Square Foot | 1190 | 0.4369% | 1983.3333 | 793.3333 | 1190 | Internal rate | [10 empty] | Upsell: stained cedar. | 1190 | 0
| SUBTOTAL: FRONT COVERED PORCH |  |  |  | 6692 | 2.457% | 11153.3333 | 4461.3333 | 6692
STRUCTURE
15 | Lumber package: framing lumber, LVLs (FB2/RB2/L1–L4), sheathing, hangers | 20 | 693 | Square Foot | 13860 | 3.983% | 18081.6833 | 7232.6733 | 10849.01 | Override | 10849.01 | 9792.11 | RONA | 9792.11 | KOTT | 10849.01 | Central Fairbank (pending) |  |  |  | Carrying KOTT (as in margin model). RONA is $1,057 lower: confirm both priced the same takeoff before award. Lumber volatile: re-quote before PO. | 9792.11 | -3010.99
16 | Framing labour: shoring, porch, 2nd floor, roof, beam install, sheathing | 22 | 693 | Square Foot | 15246 | 6.792% | 30833.3333 | 12333.3333 | 18500 | Override | 18500 | 18000 | Aryan | 18000 | Bogdan | 29000 | Built By BC | 18500 |  |  | All three bids include main-floor LVL beam install + partitions (Option B). Ask for A + beam-only price; partitions come out. Aryan is $500 below BC. | 18000 | 3254
| SUBTOTAL: STRUCTURE |  |  |  | 29106 | 10.77% | 48915.0167 | 19566.0067 | 29349.01
EXTERIOR ENVELOPE
17 | Roofing: IKO Cambridge 6:12, 2nd floor (~950 SF) + porch (~150 SF), vents, flashing | 8 | 1200 | Square Foot | 9600 | 2.267% | 10291.6667 | 4116.6667 | 6175 | Override | 6175 | 3800 | Infinity Gutters | 6175 | CA Roofing | 3800 | C A Roofing (2nd quote) | 5500 | Alps Roofing | 6350 | CA Roofing $3,800 is $2,375 below carried. Two CA quotes on file ($3,800 / $5,500): confirm which is current and that ventilation + flashing are in. | 3800 | -3425
18 | Aluminum: eaves, downspouts, soffit, fascia, window capping, flashing band at brick | 9400 | 1 | Lump Sum | 9400 | 3.056% | 13875 | 5550 | 8325 | Override | 8325 | 3800 | Infinity Gutters | 8325 | CA Roofing | 3800 |  |  |  |  | Internal = soffit/fascia $5,800 + flashing band $3,600. CA $3,800 is $4,525 lower: confirm it includes the flashing band per Sections AA/BB. | 3800 | -1075
19 | Wrap, 1" R5 rigid, Kaycan aluminum siding (~800 SF), Maibec gables, brackets, lattice | 28600 | 1 | Lump Sum | 28600 | 13.22% | 60000 | 24000 | 36000 | Low bid |  | 36000 | Infinity Gutters | 36000 | CA Roofing (declined) | [5 empty] | Only one live bid: $7,400 OVER internal. Internal = wrap $5,000 + siding 850 SF × $16 + rigid 950 SF × $4 + Maibec 200 SF × $26 + brackets/lattice ~$1,000. Get 2 more siding bids. | 36000 | 7400
20 | Windows: 6 units white vinyl casement/fixed, supply & install | 110 | 80 | Square Foot | 8800 | 2.036% | 9241.6667 | 3696.6667 | 5545 | Override | 5545 | 5221.24 | JS Windows and Doors | 5545 | Welda Windows | 5221.24 |  |  |  |  | Index $90/SF supply + $20 install. Welda $324 lower. Joist also lists windows as finish material (excluded): fix wording. | 5221.24 | -3255
| SUBTOTAL: EXTERIOR ENVELOPE |  |  |  | 56400 | 20.58% | 93408.3333 | 37363.3333 | 56045
MECHANICAL & ELECTRICAL
21 | HVAC: 2nd floor risers/trunks/diffusers, basement & main-floor changes, bath fan | 10000 | 1 | Lump Sum | 10000 | 3.084% | 14000 | 5600 | 8400 | Low bid |  | 8400 | MiTech HVAC | 8400 | Ideal Heating | 12398 | Sentral HVAC | 13479 |  |  | Low = MiTech. Bids include main-floor diffuser relocation (Option B): ask for A-only credit. MiTech also quoted Manning: same crew. | 8400 | -1600
22 | 200A service: mast, meter base, panel, Toronto Hydro, ESA | 5500 | 1 | Lump Sum | 5500 | 1.652% | 7500 | 3000 | 4500 | Low bid |  | 4500 | FV Renovations | 4500 | Renomar (included, $0) | [5 empty] | Existing panel is 100A (S1.01). Not on drawings: confirm client understands it is in scope. | 4500 | -1000
23 | Furnace / water heater re-vent (chimney removed) | 2000 | 1 | Lump Sum | 2000 | 0.7342% | 3333.3333 | 1333.3333 | 2000 | Internal rate | [10 empty] | Allowance. HWT likely vents in chimney; may need direct-vent replacement (rental?). | 2000 | 0
24 | Attic R60 blown-in + baffles | 3 | 700 | Square Foot | 2100 | 0.858% | 3895 | 1558 | 2337 | Low bid |  | 2337 | FoamIt | 2337 | [6 empty] | Wall batts are in FV's scope. | 2337 | 237
| SUBTOTAL: MECHANICAL & ELECTRICAL |  |  |  | 19600 | 6.328% | 28728.3333 | 11491.3333 | 17237
GENERAL TRADES BULK SCOPE (FV-style package)
25 | Demo, plumbing, electrical, wall insulation, drywall L4, prime, carpentry, full 2nd-floor bathroom (A only) | 53550.9 | 1 | Lump Sum | 53550.9 | 13.77% | 62500 | 25000 | 37500 | Override | 37500 | 78000 | FV Renovations (A+B) | 78000 | Renomar Inc (A+B) | 109500 |  |  |  |  | Both bids cover A + main floor (Option B). Carrying Raff's A-only number $37,500 (range $35K–$40K). Get FV's written A-only price. Internal build-up on 'FV Scope Build-up' tab. | 37500 | -16050.9
| SUBTOTAL: GENERAL TRADES BULK SCOPE (FV-style package) |  |  |  | 53550.9 | 13.77% | 62500 | 25000 | 37500
FINISHES & STAIRS
26 | Bathroom waterproofing & tile setting materials | 1200 | 1 | Lump Sum | 1200 | 0.4405% | 2000 | 800 | 1200 | Internal rate | [10 empty] | Tile is client-supplied. | 1200 | 0
27 | Quartz shower curb jamb | 400 | 1 | Lump Sum | 400 | 0.1468% | 666.6667 | 266.6667 | 400 | Internal rate | [10 empty] | Legendary $850 quote is the main-floor countertop (Option B), not this. | 400 | 0
28 | Engineered hardwood install, 2nd floor (client-supplied) | 4.5 | 600 | Square Foot | 2700 | 0.826% | 3750 | 1500 | 2250 | Low bid |  | 2250 | Reno Factory (pro-rated) | 2250 | [6 empty] | Reno Factory bid $3,000 for 800 SF both floors = $3.75/SF; 600 SF A-only = $2,250. | 2250 | -450
29 | Stair capping: treads, risers, oak stringer caps, posts, rail, pickets (S&I) | 5000 | 1 | Lump Sum | 5000 | 1.836% | 8333.3333 | 3333.3333 | 5000 | Internal rate | [10 empty] | Per Raff $5,000. No bid yet: tender it. | 5000 | 0
30 | Stair stain & varnish (one-tone) | 4500 | 1 | Lump Sum | 4500 | 2.339% | 10616.6667 | 4246.6667 | 6370 | Low bid |  | 6370 | Reno Factory | 6370 | [6 empty] | ⚠ Scope conflict: Sep 4 text says 'finishing existing stairs' included; Sep 7 email says 'removed stair finishing'. Confirm before carrying. | 6370 | 1870
31 | Aria vents (tiled) | 130 | 5 | Each | 650 | 0.2386% | 1083.3333 | 433.3333 | 650 | Internal rate | [10 empty] | Internal estimate. | 650 | 0
32 | Closet install: 2 IKEA PAX (client-supplied) | 800 | 1 | Lump Sum | 800 | 0.2937% | 1333.3333 | 533.3333 | 800 | Internal rate | [10 empty] | Allowance. | 800 | 0
| SUBTOTAL: FINISHES & STAIRS |  |  |  | 15250 | 6.12% | 27783.3333 | 11113.3333 | 16670
MAIN-FLOOR BEAM & POSTS (LVL + framing labour already in lumber/framing bids)
33 | Selective demo of bearing wall section + disposal | 1200 | 1 | Lump Sum | 1200 | 0.4405% | 2000 | 800 | 1200 | Internal rate | [10 empty] | Allowance. | 1200 | 0
34 | Basement footing pads + posts | 3000 | 1 | Lump Sum | 3000 | 1.101% | 5000 | 2000 | 3000 | Internal rate | [10 empty] | Drawings (A3.01) show posts on solid blocking to foundation wall: likely $0. Keep until site-verified. | 3000 | 0
35 | Electrical relocation out of wall | 800 | 1 | Lump Sum | 800 | 0.2937% | 1333.3333 | 533.3333 | 800 | Internal rate | [10 empty] | Allowance. | 800 | 0
36 | Drywall close-in & beam wrap, Level 4, primed | 1500 | 1 | Lump Sum | 1500 | 0.5507% | 2500 | 1000 | 1500 | Internal rate | [10 empty] | Allowance. | 1500 | 0
37 | Floor patch at old wall line | 1000 | 1 | Lump Sum | 1000 | 0.3671% | 1666.6667 | 666.6667 | 1000 | Internal rate | [10 empty] | Allowance. | 1000 | 0
38 | Engineer review | 700 | 1 | Lump Sum | 700 | 0.257% | 1166.6667 | 466.6667 | 700 | Internal rate | [10 empty] | Allowance. | 700 | 0
| SUBTOTAL: MAIN-FLOOR BEAM & POSTS (LVL + framing labour already in lumber/framing bids) |  |  |  | 8200 | 3.01% | 13666.6667 | 5466.6667 | 8200
| GRAND TOTAL (all-in cost and sell at target margin) |  |  |  | 289498.9 | 100% | 453988.35 | 181595.34 | 272393.01 | [12 empty] | 263612.35

## FV Scope Build-up
General Trades Bulk Scope: internal unit-rate build-up (2nd floor + porch + bathroom only)
Benchmarks the FV / Renomar packages. Rates: PalmView Cost Index (Manning tender) and 38 Harewood internal estimate.
# | Scope item | Unit rate | Qty | Unit | Cost | Rate source / note
1 | Demo: roof, 2nd-floor knee walls, chimney to roof level, porch + stairs, load-out | 8 | 1100 | Square Foot | 8800 | Index $14/SF was a 3rd-floor roof strip (Manning); ground-level access here.
2 | Protection: floors, stairs, dust walls | 1500 | 1 | Lump Sum | 1500 | Index: floor $3.50/SF + stairs $1,800 (Manning).
3 | Plumbing rough-in + finish: new 2nd-floor bath, tie to stack | 6000 | 1 | Lump Sum | 6000 | Internal estimate.
4 | Electrical rough-in + finish, 2nd floor (5 pots, ~20 outlets, fan, smoke/CO, bath) | 7500 | 1 | Lump Sum | 7500 | Internal estimate (2nd-floor share of $11,500).
5 | Batt insulation (R22 mineral wool) + 6-mil VB, exterior walls | 6.5 | 900 | Square Foot | 5850 | Index $6.50/SF net wall.
6 | Drywall: board, tape, plaster, sand to L4 (incl. waterproof board at shower) | 14 | 700 | Square Foot | 9800 | Index $14/SF of floor area.
7 | Prime all new drywall (no finish coat, per Sep 7 email) | 1.5 | 700 | Square Foot | 1050 | Index $1.50/SF.
8 | Baseboard + casing material (MDF) | 3.5 | 500 | Linear Feet | 1750 | Index $3.50/LF.
9 | Finish carpentry labour: base, casing, 5 doors, attic hatch, towel shelves | 85 | 40 | Hours | 3400 | Index $85/hr.
10 | Bathroom: niche, curb, shower base, waterproofing labour | 2000 | 1 | Lump Sum | 2000 | Allowance.
11 | Bathroom tile install (~270 SF, client tile) | 16.67 | 270 | Square Foot | 4500.9 | Internal $4,500 ÷ 270 SF.
12 | Bathroom fixtures, vanity, accessories, mirror install | 800 | 1 | Lump Sum | 800 | Allowance.
13 | Silicone, touch-ups, basic clean, debris removal | 600 | 1 | Lump Sum | 600 | Index (Manning).
| INTERNAL BUILD-UP TOTAL (A only) |  |  |  | 53550.9
| FV Renovations bid (A + main floor B) |  |  |  | 78000
| Renomar Inc bid (A + main floor B) |  |  |  | 109500
| Raff's FV A-only estimate (carried) |  |  |  | 37500
| Carried vs internal build-up (negative = FV below our rates) |  |  |  | -16050.9

## Option B Bids (Excluded)
Bids received for main-floor work (Option B): NOT carried in this phase
# | Scope | Bidder | Quote | Note
1 | Kitchen reface + pantry/base/island/bench cabinetry | Eureka Kitchen and Bath | 15550 | Supply + install, delivery incl. Hold for Option B price lock.
2 | Quartz countertop ~12 SF (Lucent mid-tier) | Legendary Countertops | 850 | Main-floor island.
3 | Main-floor demo, partitions, LVL beams, pot lights, drywall, paint | In FV / Renomar / framer bids |  | Main-floor share of FV $78,000 est. ~$16K; ask each bidder to split A vs B.
4 | Main-floor flooring install (~600 SF) | Reno Factory | 750 | Balance of $3,000 bid (800 SF × $3.75) not used for A.

## Flags & Next Steps
Bid gaps, scope conflicts and actions before award
# | Item | Action
1 | Siding / envelope: one live bid only | Infinity $36,000 vs internal $28,600 (+$7,400). Send to 2 more siding subs (same scope as Bid Request #10).
2 | Porch piers: no prices back | MBS, Windmill, Msix all pending. Chase this week; Raff number $2,000 carried via internal rate.
3 | Lumber: Central Fairbank pending | Confirm RONA vs KOTT priced the same takeoff; RONA $1,057 lower. Re-quote before PO (lumber volatile).
4 | Framing bids include Option B | Ask Aryan / BC for A + beam-only price (main-floor partitions + joist reinforcement come out). Aryan $500 below BC.
5 | General trades bids are A+B | FV $78K and Renomar $109.5K include the main floor. Get written A-only prices; $37,500 carried per Raff.
6 | HVAC bids include main-floor diffuser moves | Ask MiTech for A-only credit (diffuser 7 + low-wall relocations).
7 | Roofing / aluminum low bids (CA Roofing) | CA $3,800 roofing and $3,800 aluminum are well below carried. Confirm scope parity (vents, flashing band) then decide. Potential saving ≈ $6,900.
8 | Stair finishing conflict | Sep 4 text: finishing included. Sep 7 email: stair finishing removed. Joist: included. Decide, then align Joist + carried cost.
9 | Bathroom: shower-only vs tub | Sep 7 email says shower-only; Joist still lists drop-in tub/deck. Clean up Joist.
10 | Beam footings | A3.01 shows posts on blocking to foundation wall: $3,000 allowance likely drops to $0 once verified.
11 | Water heater / chimney | Confirm what vents in the chimney; allowance $2,000 may not cover a direct-vent HWT if owned (not rental).
12 | Pricing vs 40% target | See Summary: current price is far below a 40% margin once PM, labour and overhead are included. Decide the margin basis before re-issuing the Joist.