## Summary
38 Harewood Ave — Second Floor, Porch & Beam ¦ Internal Margin Model
Julianne & David Lee · PalmView Contracting Inc. · Prepared Oct 16, 2026 · INTERNAL — DO NOT SEND TO CLIENT · Blue text = editable input
PROJECT INPUTS
Input | Value |  | Source / note
Construction start date | 2027-05-17 |  | Joist 110-351 schedule (~May 17, 2027). Change here — schedule updates automatically.
Duration (weeks) | 24 |  | Linked to Schedule tab (sum of phases). Edit phase weeks there.
Substantial completion (est.) | 2027-10-29 |  | Start + duration, ending on a Friday.
Duration (months, approx.) | 5.5427
Option A contract price (pre-HST) | 271379.75 |  | Joist estimate 110-351: Section 2.0 $269,754.25 + service fee $1,625.50.
Beam & posts price (pre-HST) | 16500 |  | Recommended price to client for main-floor beam/posts only.
HST rate | 13% |  | Ontario HST.
FV Renovations — general trades (2nd floor + porch) | 37500 |  | Per Raff: $35K–$40K. Midpoint used. Get FV's written A-only price.
Project management ($/week) | 1700 |  | Sean's budgeting sheet rate.
Site labour ($/week) | 600 |  | Sean's budgeting sheet rate.
Overhead ($/week) | 1000 |  | Per Raff: insurance, WSIB, office, vehicles, software.
PROFIT SUMMARY (BASE — NO OFFERS)
Line | Amount | % of price | How it's calculated
Option A contract (2nd floor, bath, porch) | 271379.75 | 94.27% | Joist 110-351
Beam & posts | 16500 | 5.732% | Input
CONTRACT PRICE (pre-HST) | 287879.75 | 100%
HST | 37424.3675 | 13%
CLIENT TOTAL (incl. HST) | 325304.1175 | 113%
Hard cost — 2nd floor & porch | 184501 | 64.09% | Costs tab
Beam & posts — added cost | 8200 | 2.848% | Costs tab
Project management | 40800 | 14.17% | Rate × weeks
Site labour | 14400 | 5.002% | Rate × weeks
Overhead | 24000 | 8.337% | Rate × weeks
TOTAL COST | 271901 | 94.45%
NET PROFIT | 15978.75 | 5.55%
Margin (profit ÷ price) | 5.55%
Markup (profit ÷ cost) | 5.877%
Weekly carrying cost (PM + labour + overhead) | 3300 |  | Every extra week costs this
WITH SELECTED OFFERS, UPSELLS & COST SAVINGS (Offers tab — set Y/N)
Line | Amount | % of price | Note
Price change from selected items | 0 | 0%
Cost change from selected items | 7500 | 2.605%
ADJUSTED CONTRACT PRICE (pre-HST) | 287879.75 | 100%
ADJUSTED TOTAL COST | 279401 | 97.05%
ADJUSTED NET PROFIT | 8478.75 | 2.945%
Adjusted margin | 2.945%
Adjusted markup | 3.035%
Profit change vs. base | -7500 | -2.605%
PRICE NEEDED FOR TARGET MARGIN (at base cost)
Target margin | Price (pre-HST) | vs. current | Note
15% | 319883.5294 | 32003.7794 | Positive = how much the price would need to go up.
20% | 339876.25 | 51996.5
25% | 362534.6667 | 74654.9167
Formulas:
Value = B6+[Value, row above]*7-3

## Costs
Cost Breakdown — All PalmView Costs
Bids = approved JobTread bids on job #6 'Harewood Avenue: Home Addition'. Blue = editable. Finish materials are client-supplied (see Exclusions).
# | Category | Item | Source | Cost ($) | Notes
1 | General conditions | Temporary hoarding & safety fencing | Internal estimate | 3000
2 | General conditions | Temporary toilet & temporary hydro | Internal estimate | 3500
3 | General conditions | Misc. supplies, materials & garbage | Internal estimate | 2000 | FV bid includes the disposal bin.
4 | General conditions | Safety supplies & third-party inspections | Internal estimate | 2500
5 | General conditions | Scaffold / lift rental | Allowance | 2500 | Second-floor exterior work.
6 | General conditions | Weather protection while roof is off | Allowance | 1500 | Tarps, temporary roof.
7 | General conditions | Engineer field reviews | Allowance | 1500 | Piers, framing per S1.01.
8 | Porch | Concrete piers (porch) | Per Raff | 2000 | Pier bids pending in JobTread.
9 | Porch | PT framing, decking & railing material | Allowance | 3500 | Framer bid is labour only.
10 | Porch | T&G porch ceiling | Allowance | 1200
11 | Structure | Lumber package (framing, LVLs, sheathing, hardware) | KOTT bid | 10849 | RONA $9,792 also approved.
12 | Structure | Framing labour (shoring, porch, 2nd floor, roof, beam install) | Built By BC bid | 18500 | Aryan $18,000 / Bogdan $29,000.
13 | Exterior | Roofing — IKO Cambridge, 2nd floor + porch | Infinity Gutters bid | 6175 | CA Roofing $3,800 available (Offers tab).
14 | Exterior | Aluminum — soffit, fascia, eaves, capping, flashing band | Infinity Gutters bid | 8325 | CA Roofing $3,800 available (Offers tab).
15 | Exterior | Wrap, R5 rigid, Kaycan siding, Maibec, brackets, lattice | Infinity Gutters bid | 36000
16 | Exterior | Windows — 6 units, supply & install | JS Windows bid | 5545 | Welda $5,221 available. Confirm Joist supply vs. exclusion.
17 | Mechanical | HVAC — 2nd floor, basement, main-floor diffusers, bath fan | MiTech HVAC bid | 8400 | Ideal $12,398 / Sentral $13,479 — risk if MiTech drops.
18 | Mechanical | Furnace / water heater re-vent (chimney removed) | Allowance | 2000 | Confirm on site whether they vent through chimney.
19 | Electrical | 200A service, mast, panel, Toronto Hydro, ESA | FV Renovations bid | 4500
20 | General trades | FV — demo, plumbing, electrical, wall insulation, drywall, paint, carpentry, full bathroom | Per Raff (Summary B13) | 37500 | Linked to Summary input. FV full A+B bid was $78,000.
21 | Insulation | Attic R60 blown-in + baffles | FoamIt bid | 2337
22 | Bathroom | Waterproofing & tile setting materials | Allowance | 1200 | Tile itself is client-supplied.
23 | Bathroom | Quartz shower curb jamb | Allowance | 400
24 | Finishes | Engineered hardwood install — 2nd floor (~600 sf) | Reno Factory bid (pro-rated) | 2250 | Bid was $3,000 for both floors.
25 | Finishes | Stair capping — treads, risers, oak caps, posts, rail, pickets | Per Raff | 5000
26 | Finishes | Stair stain & varnish (one-tone) | Reno Factory bid | 6370
27 | Finishes | Aria vents | Internal estimate | 650
28 | Finishes | Closet install — 2 IKEA PAX (client-supplied) | Allowance | 800
29 | Completion | Final clean, deficiencies, final inspections | Internal estimate | 4500
|  | HARD COST TOTAL — 2nd floor & porch |  | 184501
BEAM & POSTS — ADDED COST (LVL + framing labour already in KOTT and Built By BC bids)
# | Category | Item | Source | Cost ($) | Notes
1 | Beam | Selective demo of wall section + disposal | Allowance | 1200
2 | Beam | Basement footing pads + posts | Allowance | 3000 | Only if the engineer requires. Set to 0 if not.
3 | Beam | Electrical relocation out of wall | Allowance | 800
4 | Beam | Drywall close-in & beam wrap, Level 4, primed | Allowance | 1500
5 | Beam | Floor patch at old wall line | Allowance | 1000
6 | Beam | Engineer review | Allowance | 700
|  | BEAM & POSTS TOTAL |  | 8200
TIME-BASED COSTS (from Summary rates × duration)
# | Category | Item | Rate / week | Cost ($) | Notes
1 | Time-based | Project management | 1700 | 40800 | × 24 weeks
2 | Time-based | Site labour | 600 | 14400 | × 24 weeks
3 | Time-based | Overhead | 1000 | 24000 | × 24 weeks
|  | TIME-BASED TOTAL |  | 79200
|  | ALL-IN PROJECT COST |  | 271901
EXCLUSIONS (put in writing)
• Shower glass (~$2,000 cost if added later)
• All finish materials: flooring, tile, plumbing fixtures, lighting, interior doors, closets, mirror & accessories
• All main-floor work except the beam & posts (Option B deferred)
• Permit, city and development fees; Builder's Risk insurance (client)
• Designated substance survey / asbestos or vermiculite abatement
• Furnace rebalancing; temporary heat (budget ~$4,000 if job runs into late fall)

## Offers
Offers, Bargaining Chips, Upsells & Cost Savings
Set column G to Y to include an item — Summary rows 38–45 update. Price/cost figures for upsells are estimates; confirm with trades before quoting.
Airbnb / rental rate ($/month) |  | 4500 | Furnished 3-bed near Cliffcrest/Bluffs: ~$4,000–$5,500/mo (REW, liv.rent, Oct 2026)
Months of rental covered |  | 3
Move-out credit ($/month, capped) |  | 2500
Price discount (%) |  | 2%
Type | Item | Price to client | Cost to PalmView | Profit impact | Margin if only this | Include? (Y/N) | Price applied | Cost applied | Notes
Bargaining chip | Move-out credit (capped, tied to signing + vacant start) | 0 | 7500 | -7500 | 2.945% | Y | 0 | 7500 | Recommended closer.
Bargaining chip | Airbnb / short-term rental covered | 0 | 13500 | -13500 | 0.861% | N | 0 | 0 | Use only if needed to win against another builder.
Bargaining chip | Airbnb for full duration | 0 | 24942.2633 | -24942.2633 | -3.114% | N | 0 | 0 | Not recommended — exceeds most of the profit.
Bargaining chip | Price discount | -5757.595 | 0 | -5757.595 | 3.623% | N | 0 | 0
Bargaining chip | Beam & posts at cost | -8300 | 0 | -8300 | 2.747% | N | 0 | 0 | Gives away beam profit.
Bargaining chip | Shower glass included (no charge) | 0 | 2000 | -2000 | 4.856% | N | 0 | 0 | Currently excluded.
Bargaining chip | Lock Option B price if started within 3 months of completion | 0 | 0 | 0 | 5.55% | N | 0 | 0 | No cost now — strong closer.
Bargaining chip | Extended labour warranty (2 → 3 years) | 0 | 1000 | -1000 | 5.203% | N | 0 | 0 | Allowance for callbacks.
Upsell | EV charger rough-in (uses new 200A service) | 1800 | 1000 | 800 | 5.792% | N | 0 | 0 | Estimate.
Upsell | Main-floor pot light pre-wire while wall is open (~10) | 2500 | 1400 | 1100 | 5.882% | N | 0 | 0 | Estimate. Saves cost in Option B later.
Upsell | Stained cedar porch ceiling (vs. standard T&G) | 2200 | 1300 | 900 | 5.819% | N | 0 | 0 | Estimate.
Upsell | Aluminum/steel porch railing (30 LF) vs. PT wood | 6500 | 4200 | 2300 | 6.209% | N | 0 | 0 | Estimate.
Upsell | Cat6 + security camera pre-wire | 1800 | 900 | 900 | 5.827% | N | 0 | 0 | Estimate.
Upsell | Shower glass — PalmView supply & install | 3000 | 2000 | 1000 | 5.837% | N | 0 | 0 | Cost per Raff $2,000.
Upsell | Spray foam at rim joists / band (air-sealing upgrade) | 2500 | 1500 | 1000 | 5.847% | N | 0 | 0 | Estimate.
Cost saving | CA Roofing $3,800 instead of Infinity roofing $6,175 | 0 | -2375 | 2375 | 6.375% | N | 0 | 0 | Both bids approved — confirm scope.
Cost saving | CA Roofing aluminum $3,800 instead of Infinity $8,325 | 0 | -4525 | 4525 | 7.122% | N | 0 | 0 | Both bids approved — confirm scope.
Cost saving | Welda windows $5,221 instead of JS $5,545 | 0 | -324 | 324 | 5.663% | N | 0 | 0
Cost saving | No basement footings needed under beam | 0 | -3000 | 3000 | 6.593% | N | 0 | 0 | Pending engineer.
| TOTAL OF SELECTED ITEMS |  |  | -7500 |  |  | 0 | 7500
| Adjusted margin (see Summary) |  |  | 2.945%

## Schedule
Schedule & Start Date
Phase weeks in blue drive the duration, PM, site labour and overhead. Phases shown sequentially; exterior and interior work can overlap to shorten the job.
# | Construction phase | Weeks | Start | Finish | Notes
1 | Mobilization; demo roof, 2nd floor, chimney; porch demo | 2 | 2027-05-17 | 2027-05-28 | Clients moved out before this date.
2 | Porch piers; main-floor shoring, beam & posts; basement point loads | 2 | 2027-05-31 | 2027-06-11 | Engineer review.
3 | Second-floor framing, roof structure, sheathing & dry-in | 5 | 2027-06-14 | 2027-07-16
4 | Roofing, windows, house wrap | 2 | 2027-07-19 | 2027-07-30
5 | Rough-ins: plumbing, HVAC, electrical, 200A service + inspections | 3 | 2027-08-02 | 2027-08-20 | Toronto Hydro disconnect/reconnect.
6 | Insulation & drywall (Level 4) | 3 | 2027-08-23 | 2027-09-10 | Insulation inspection.
7 | Bathroom tile, flooring, stairs, trim & paint | 4 | 2027-09-13 | 2027-10-08 | Client finish selections must be on site.
8 | Siding, Maibec, aluminum, porch finishing | 2 | 2027-10-11 | 2027-10-22 | Can overlap interior phases.
9 | Final fixtures, deficiencies, final inspections, clean | 1 | 2027-10-25 | 2027-10-29
| TOTAL DURATION (weeks) | 24 | 2027-05-17 | 2027-10-29
PRE-CONSTRUCTION TARGETS (estimates — confirm with Mark and the City)
# | Milestone |  | Target date |  | Notes
1 | Site visit with Julianne & David |  | 2026-10-16 |  | Today 4–5pm.
2 | Engineer confirms beam/post load path |  | 2026-11-13
3 | Mark revises drawings (2nd floor, porch, beam only) |  | 2026-11-27
4 | Permit submission to City of Toronto |  | 2026-12-04
5 | Revised estimate signed + deposit |  | 2027-01-15 |  | Locks the May start.
6 | Permit issued (est.) |  | 2027-03-31 |  | Toronto residential additions often take 2–4 months.
7 | Client finish selections complete |  | 2027-04-15
8 | Clients move out |  | 2027-05-15 |  | Weekend before start.
9 | Construction start |  | 2027-05-17
10 | Substantial completion |  | 2027-10-29
Formulas:
Start = [Finish, row above]+3
Finish = [Start]+[Weeks]*7-3

## Duration vs Margin
Duration vs. Margin — what each week costs
Base case, no offers. Uses Summary rates and costs; FV price varies across columns. Contract price fixed at Summary B22.
FV price → | 35000 | 37500 | 40000 | 35000 | 37500 | 40000
Weeks | Margin | Margin | Margin | Net profit | Net profit | Net profit
12 | 20.17% | 19.31% | 18.44% | 58078.75 | 55578.75 | 53078.75
16 | 15.59% | 14.72% | 13.85% | 44878.75 | 42378.75 | 39878.75
20 | 11% | 10.14% | 9.267% | 31678.75 | 29178.75 | 26678.75
24 | 6.419% | 5.55% | 4.682% | 18478.75 | 15978.75 | 13478.75
28 | 1.834% | 0.9652% | 0.09683% | 5278.75 | 2778.75 | 278.75
32 | -2.752% | -3.62% | -4.488% | -7921.25 | -10421.25 | -12921.25
Red = under 10% margin · Green = 20%+ margin