## Construction Plan
439 Manning Ave: Construction Plan
Kyle Luong & Nancy Song ¦ Third-floor rear addition + bedroom reconfiguration ¦ PalmView Contracting Inc. ¦ Prepared for Raff Di Palma
PROJECT SUMMARY
Address | 439 Manning Ave, Toronto, ON M6G 2V6
JobTread job | #5 Manning Ave: Home Addition
Scope | New ~245 sq ft third-floor rear lounge over the existing 2nd-storey flat roof, sitting room converted to a bedroom, hall. 405.66 sq ft finished. No foundation work, no plumbing.
Contract signed | New Addition Proposal, issued Apr 3, 2026 (JobTread doc #1)
Excluded from base | Windows and exterior doors (supply + install), and all finish materials: hardwood, interior doors, hardware. Client-paid.
Project manager | David Magarici
Architect / design | Pino (La Vecchia Designs)
STATUS (as of Oct 20, 2026)
Item | Detail | Status
Committee of Adjustment | Approved Sep 23, 2026 (client notified Sep 25). Neighbour support letters on file. | Done
Zoning review (permit drawings) | Submitted. Response expected about Oct 27. | In progress
Building permit | Not yet applied for. Apply as soon as zoning clears. | Not started
Tendering | Bids in for most divisions; Fabiano, Doctor Demo and New Age still pending. Deadline Thu Oct 22, 7 PM (David). | In progress
Construction schedule | Draft below. David to finalize with trades by Thu Oct 22, 7 PM. | In progress
Start date communicated to client | Aug 17: end of Oct / early Nov (tentative). Kyle asked again Oct 13; no firm date sent yet. | Action needed
FINANCIAL SNAPSHOT (live from the Finances tabs)
Contract total (pre-HST) | 123030.16
Base scope sell: 2.0 Rear Addition | 114070
Cost target at 35% markup | 84496.2963
Base cost: current bids (Renomar) | 122296.69
Base cost: Fabiano scenario | 85196.69
Margin: current bids | -7.212%
Margin: Fabiano scenario | 25.31%
All-in margin, Fabiano (incl. contingency + provisional) | 13.46%
Collected to date (incl. HST) | 6951.204
Still to invoice (incl. HST) | 132072.8768
KEY RISKS AND DECISIONS
1. | Fabiano's General Works price decides the margin. Confirm it includes demo, licensed electrical + ESA, and drywall/insulation/trim materials.
2. | Brick veneer add-on: lowest bid $31,200 vs about $8,000 told to the client. Re-quote before Kyle, Nancy or neighbour Peter commit.
3. | Interior brick wall add-on: $10,800 bid vs about $3,600 quoted to the client.
4. | Structural engineering not yet issued. Reinforcement below is a change order per contract ($5,000 provisional carried).
5. | Winter build: the roof is open from demo until the flat roof is on (about 4.5 weeks in Jan to Feb). Budget temporary heat and weather protection, or hold demo until the permit date is firm.
6. | Bedroom egress window and side-wall limiting distance to be confirmed with the designer before windows are ordered.
7. | Window lead time drives the schedule. Client must order as soon as sizes are locked off framing.

## Schedule
439 Manning Ave: Construction Schedule (draft)
Durations are planning estimates. David to confirm each one with the trade by Thu Oct 22. Change the yellow cells; dates update.
Expected permit issue date | 2026-12-04 | Estimate: zoning response ~Oct 27, then permit application; City review assumed ~5 weeks. Replace with the real date.
Mobilization lead after permit (days) | 7 | Time to book trades, bin, scaffold and protection after permit.
Construction start | 2026-12-11
Substantial completion | 2027-05-09
Total duration (weeks) | 21
# | Phase / task | Trade | Duration (weeks) | Start | Finish | Inspection / milestone | Payment milestone
1 | Mobilize: protection, bin, scaffold, portable toilet | PalmView / Site services | 1 | 2026-12-11 | 2026-12-18 |  | Construction Start (15%)
2 | Holiday shutdown: roof stays closed until the new year | None | 2.5 | 2026-12-18 | 2027-01-05
3 | Demolition: rear roof removal + temporary weather protection | Fabiano / demo contractor | 1 | 2027-01-05 | 2027-01-12
4 | Framing: floor system, walls, flat roof, beams, ridge raise | Aryan (framing) + lumber | 3 | 2027-01-12 | 2027-02-02 | Framing inspection | Framing Complete (30%)
5 | Flat roofing, parapet flashing, skylight | Safety Roofing | 1.5 | 2027-02-02 | 2027-02-13
6 | Window install (client-supplied units) | Window supplier | 1 | 2027-02-13 | 2027-02-20
7 | Siding / cladding + flashing | Safety Roofing | 2 | 2027-02-20 | 2027-03-06
8 | HVAC rough-in + electrical rough-in | Ideal Heating / Fabiano electrician | 1.5 | 2027-03-06 | 2027-03-17 | ESA rough-in inspection | Electrical Rough-ins Complete (15%)
9 | Spray foam (roof) + batt insulation + vapour barrier | FoamIt / Fabiano | 1 | 2027-03-17 | 2027-03-24 | Insulation inspection
10 | Drywall: board, tape, plaster, sand, prime | Fabiano | 2 | 2027-03-24 | 2027-04-07 |  | Drywall Boarding Complete (10%)
11 | Painting: finish coats | Fabiano | 1 | 2027-04-07 | 2027-04-14
12 | Hardwood flooring + trim + interior doors (client-supplied) | Fabiano | 1.5 | 2027-04-14 | 2027-04-25 |  | Flooring Installed (10%)
13 | HVAC + electrical finish, devices, commissioning | Ideal Heating / Fabiano electrician | 1 | 2027-04-25 | 2027-05-02 | ESA final
14 | Punch list, clean-up, strip protection | Fabiano / PalmView | 1 | 2027-05-02 | 2027-05-09 | Final building inspection | Punch List (5%)
Tasks run one after another, which is conservative. Overlaps (e.g. siding while roughing in) can shorten it once David confirms crews. Weeks are calendar weeks, Monday to Friday site hours (T&C 16.1).
Formulas:
Start = [Finish, row above]
Finish = [Start]+ROUND([Duration (weeks)]*7,0)

## Payment Schedule
439 Manning Ave: Client Payment Schedule
Contract milestones from JobTread invoices #2 to #9. Paid / status per JobTread on Oct 20, 2026.
Contract total (pre-HST) | 123030.16 | JobTread New Addition Proposal (doc #1), approved. Includes design fees.
HST rate | 13%
Design fees + other (contract total less base scope sell) | 8960.16
Milestone | % of contract | Amount (pre-HST) | HST | Total incl. HST | Status | Collected (incl. HST) | To invoice (incl. HST) | Expected date
Deposit | 5% | 6151.508 | 799.696 | 6951.204 | Paid | 6951.204 | 0 | Jul 10, 2026 (invoiced)
Building Permit Submission | 10% | 12303.016 | 1599.3921 | 13902.4081 | Draft | 0 | 13902.4081 | When permit is applied for
Construction Start Date | 15% | 18454.524 | 2399.0881 | 20853.6121 | Draft | 0 | 20853.6121 | 2026-12-11
Framing Complete | 30% | 36909.048 | 4798.1762 | 41707.2242 | Draft | 0 | 41707.2242 | 2027-02-02
Electrical Rough-ins Complete | 15% | 18454.524 | 2399.0881 | 20853.6121 | Draft | 0 | 20853.6121 | 2027-03-17
Drywall Boarding Complete | 10% | 12303.016 | 1599.3921 | 13902.4081 | Draft | 0 | 13902.4081 | 2027-04-07
Flooring Installed | 10% | 12303.016 | 1599.3921 | 13902.4081 | Draft | 0 | 13902.4081 | 2027-04-25
Punch List | 5% | 6151.508 | 799.696 | 6951.204 | Draft | 0 | 6951.204 | 2027-05-09
TOTAL | 100% | 123030.16 | 15993.9208 | 139024.0808 |  | 6951.204 | 132072.8768
Milestones add to 100%
Status values: Paid or Draft. Invoices are due within 2 calendar days of issue (T&C 9.1).

## Leveling
439 Manning Ave: Base Scope Bid Leveling vs Budget and 35% Markup Target
Scenario: Fabiano at $20,000 incl. demo ¦ Roof/siding: Safety
Division | Budget (cost) | Lowest approved bid | Low bidder | Current: Renomar | Scenario: Fabiano | Scenario vs budget | # prices in | # required (SOP)
General Works (bulk) | 30041 | 57100 | Renomar Inc (Olimpiu) | 57100 | 20000 | -10041 | 1 | 4
Demolition (separate line) | 6290 | 0 | No price yet | 0 | 0 | -6290 | 0 | 3
Framing & Structure | 23128 | 14000 | Aryan | 14000 | 14000 | -9128 | 1 | 3
Lumber Supply | 4900 | 6386.19 | RONA (Jonathan) | 6386.19 | 6386.19 | 1486.19 | 3 | 3
Flat Roofing | 8010 | 15700 | Alps Roofing | 0 | 0 | 0 | 1 | 3
Siding / Cladding | 17750 | 7900 | Baz Aluminum | 0 | 0 | 0 | 1 | 3
Roof + Siding Combo (Safety) | 0 | 20580 | Safety Roofing (Elvis) | 20580 | 20580 | -5180 | 1 | 1
HVAC: Mini-Split | 6750 | 9370 | Ideal Heating (Leena) | 9370 | 9370 | 2620 | 2 | 3
Spray Foam | 3430 | 3360.5 | FoamIt (Nadia) | 3360.5 | 3360.5 | -69.5 | 1 | 3
Site Services & Hoisting | 11500 | 0 | No price yet: budget carried | 11500 | 11500 | 0 | 0 | 1
BASE COST TOTAL | 111799 |  |  | 122296.69 | 85196.69 | -26602.31
MARGIN CHECK |  |  |  | Current: Renomar | Scenario: Fabiano
Contract sell (pre-HST) |  |  |  | 114070 | 114070
Cost target = sell / (1 + markup) |  |  |  | 84496.2963 | 84496.2963
Base cost (from total above) |  |  |  | 122296.69 | 85196.69
Over / (under) cost target |  |  |  | 37800.3937 | 700.3937
Gross profit |  |  |  | -8226.69 | 28873.31
Margin (profit / sell) |  |  |  | -7.212% | 25.31%
Markup (profit / cost) |  |  |  | -6.727% | 33.89%
Target margin at that markup |  |  |  | 25.93% | 25.93%
RISK VIEW: + contingency + provisional
Contingency |  |  |  | 12229.669 | 8519.669
Provisional: structural reinforcement |  |  |  | 5000 | 5000
All-in cost |  |  |  | 139526.359 | 98716.359
All-in profit |  |  |  | -25456.359 | 15353.641
All-in margin |  |  |  | -22.32% | 13.46%
ADD-ONS: bid vs what the client was told
Add-on | Budget (cost) | Lowest bid | Low bidder | Client was told (sell) | Sell at 35% markup | Gap: needed sell - told
Brick Veneer (exterior) | 36400 | 31200 | Amoroso Construction | 8000 | 42120 | 34120
Rustic Interior Brick Wall | 3960 | 10800 | Amoroso Construction | 3600 | 14580 | 10980
Angled Skylight | 4600 | 3300 | Skylight Services Ltd | 2500 | 4455 | 1955
Windows: CLIENT-PAID, NOT IN BASE COST (info only) | 8470 | 7850 | JS Windows and Doors
Finish materials: CLIENT-PAID, NOT IN BASE COST (hardwood, interior doors, hardware) | 7549 |  | Tender Package P9 budget; client selections
Notes
Amounts come from the cost field on each JobTread bid request. Quote PDFs not reviewed, so scope inclusions and HST treatment are unconfirmed.
Contract sell $114,070 is the 2.0 Rear Addition base only (excludes design fees and add-ons), per the Tender Package margin check.
Base cost EXCLUDES windows (supply + install) and all client finish materials (hardwood, interior doors, hardware). Base includes only the install labour for hardwood, doors and trim inside General Works.
Confirm Renomar's and Fabiano's prices do NOT include supply of hardwood, interior doors or hardware, or window install. If they do, deduct it.
Safety Roofing combo includes the skylight (an add-on), so the base is slightly overstated when Safety is selected. That's conservative.
Site Services has no quote yet; the $11,500 budget is carried at cost.
Confirm with Fabiano: demo as a separate line, licensed electrician + ESA included, and materials (drywall, insulation, trim) included.
Note on A6: Renomar's $57,100 covers General Works + Demo, so demo is $0 in the Current column. In the Fabiano scenario, demo is $0 if Inputs says his price includes it; otherwise the demo cost from Inputs is added.
Note on A14: No quote yet. Budget is carried at cost in both columns until rental quotes come in.
Note on A21: Positive = over the cost target (bad). Zero or negative = within tolerance.
Note on A36: Budget is the net brick delta over vinyl ($48,750 brick less $12,350 vinyl credit). Client told about $8,000.
Note on A37: Client quoted about $3,600 sell.
Note on A38: Client told $2K to $3K incl. labour; midpoint used. Aluplex $300 excluded as a partial price (see All Bids).
Note on B40: Client budget for windows. Supply AND install are excluded from the contract (General Note 3). Window bids are tendered only so the client can order and we can lock the schedule.
Note on E5: Renomar's approved bid covers General Works + Demo combined.
Note on G11: When Safety is selected, the combo is compared against the Flat Roofing + Siding budgets combined ($25,760), and those two rows show no variance. The combo also includes the skylight.

## Inputs
439 Manning Ave: Bid Leveling Inputs
Yellow cells are the levers. Change them and every tab updates. Blue = typed-in number, black = formula, green = pulled from another tab.
Input | Value | Source / note
Contract sell: 2.0 Rear Addition (pre-HST) | 114070 | Tender Package, Margin Check (from invoice #22288). Excludes design fees and add-ons.
Target markup on cost (SOP Step 5) | 35% | Tendering SOP: cost target = contract sell / 1.35.
Fabiano General Works price (estimate) | 20000 | Raff's estimate, Oct 20. Replace with the real number when it comes in.
Does Fabiano's price include demolition? (Yes/No) | Yes | The work order asks for demo as a separate line. If No, the demo cost below gets added.
Demolition cost if separate | 6290 | Internal demo budget (P7D). Replace with Fabiano's or Doctor Demo's price.
Roof + siding option (Split / Safety) | Safety | Split = Alps roof + Baz siding. Safety = Safety Roofing combo (siding, flat roof and skylight).
Construction contingency (% of cost) | 10% | Tender Package: 10% budget reserve.
Provisional: structural reinforcement | 5000 | Tender Package P2 provisional / change order risk.

## All Bids
All Manning Bid Requests (from JobTread, Oct 20, 2026)
Amounts are the cost entered on each JobTread bid request. HST treatment not confirmed. To add a bid, insert a row above the last one and copy column E down.
Division | Vendor | Status | Amount ($) | Lookup key (formula) | JobTread #
General Works + Demo | Renomar Inc (Olimpiu) | Approved | 57100 | General Works + Demo¦57100 | 46
General Works + Demo | FV Renovations (Fabiano) | Pending | 0 |  | 15
Demolition | Doctor Demo (Roman) | Pending | 0 |  | 10
Demolition | Bradley Demolition | Declined | 0 |  | 41
Demolition | Universal Impact Services | Declined | 0 |  | 42
Framing | Aryan | Approved | 14000 | Framing¦14000 | 31
Framing | New Age Construction (Mario) | Pending | 0 |  | 17
Framing | Bogdan | Declined | 0 |  | 30
Lumber | RONA (Jonathan) | Approved | 6386.19 | Lumber¦6386.19 | 43
Lumber | Central Fairbank (Bruno) | Approved | 7040 | Lumber¦7040 | 50
Lumber | KOTT (Jon Stark) | Approved | 7208.9 | Lumber¦7208.9 | 45
Flat Roofing | Alps Roofing | Approved | 15700 | Flat Roofing¦15700 | 21
Flat Roofing | CA Roofing (Jason) | Declined | 0 |  | 32
Flat Roofing | Ebi | Declined | 0 |  | 33
Siding | Baz Aluminum | Approved | 7900 | Siding¦7900 | 38
Siding | SM Cladding (Milos) | Declined | 0 |  | 39
Roof + Siding + Skylight Combo | Safety Roofing (Elvis) | Approved | 20580 | Roof + Siding + Skylight Combo¦20580 | 49
HVAC | Ideal Heating (Leena) | Approved | 9370 | HVAC¦9370 | 28
HVAC | MiTech HVAC (Mikel) | Approved | 9950 | HVAC¦9950 | 18
HVAC | Sentral HVAC | Declined | 0 |  | 27
HVAC | MMS HVAC | Declined | 0 |  | 29
Spray Foam | FoamIt (Nadia) | Approved | 3360.5 | Spray Foam¦3360.5 | 13
Windows (client-paid) | JS Windows and Doors | Approved | 7850 | Windows (client-paid)¦7850 | 16
Windows (client-paid) | Kingshore Windows | Approved | 8340 | Windows (client-paid)¦8340 | 47
Windows (client-paid) | WELDA Windows & Doors | Approved | 9646.02 | Windows (client-paid)¦9646.02 | 37
Add-on: Brick Veneer | Amoroso Construction | Approved | 31200 | Add-on: Brick Veneer¦31200 | 12
Add-on: Interior Brick | Amoroso Construction | Approved | 10800 | Add-on: Interior Brick¦10800 | 14
Add-on: Skylight | Skylight Services Ltd | Approved | 3300 | Add-on: Skylight¦3300 | 24
Add-on: Skylight | Aluplex | Approved (partial) | 300 |  | 26
Hardwood Install (in GW scope) | Reno Factory (Roland) | Approved | 1215 | Hardwood Install (in GW scope)¦1215 | 22
Note on C33: Marked Approved in JobTread, but $300 looks like a partial price (unit only?). Excluded from the low-bid lookup. Change the status to Approved to include it.