PalmView Contracting Inc.

Scope of Work & Quotation — New Two-Storey Single Detached Dwelling

Project: 94 Margaret Ave, Stoney Creek (Hamilton), ON

Date: October 21, 2026  |  Valid until: November 5, 2026 (15 days)

Basis: Bobicon Ltd. architectural set SP1, A0.1–A6.0 (April 9, 2026) and AM Engineering Grading Plan, Project 26047, Rev. 3 (Sept 30, 2026).

House size: 2,930 SF finished (main 1,460 SF + second 1,470 SF), 1,460 SF unfinished basement, 548 SF two-car garage, 60 SF covered front porch, 204 SF covered rear patio.

PROJECT SUMMARY

PalmView will demolish the existing dwelling and build a new two-storey home with basement and attached two-car garage, complete to drywall (Level 4, unprimed) under a fixed price. Specifications are entry level throughout: vinyl double-pane windows, insulated steel doors, asphalt shingles, brick/stone and stucco cladding as drawn. The basement is left unfinished. Finishes needed to complete the home are listed separately as an optional entry-level Finished Material Budget.

BLOCK 1 — OWNER DIRECT COSTS (AT COST, NO MARKUP)

Pay City of Hamilton building permit fees for the new dwelling and grading review.

Pay City of Hamilton development charges. Carried assuming a demolition credit for the existing house; amount to be confirmed with the City.

Pay utility connection fees for water, sewer, gas and hydro services.

These are pass-through amounts. Actual invoices are billed at cost and adjusted up or down at closeout.

Block 1 — Owner Direct Costs: $72,000

BLOCK 2 — FIXED COST (THROUGH DRYWALL)

PRE-CONSTRUCTION SCOPE

Prepare and submit the City permit package and coordinate the permit through issuance with the designer and engineer.

Provide structural engineering, HVAC design and heat loss / SB-12 energy compliance, and truss layout drawings.

Arrange surveyor stakeout, footing and wall pins, and foundation location survey.

Arrange AM Engineering site reviews for servicing and lot grading.

Complete a designated substance survey of the existing house before demolition; carry a provisional abatement allowance.

Install City tree protection hoarding, temporary construction fence, toilet, hydro and water.

Provide temporary heat during winter months, scaffold for masonry and stucco, and a crane to set roof trusses.

Provide waste bins, site safety, signage, sidewalk/road protection, utility locates and builder's risk insurance.

Enrol the home with Tarion.

Provide full-time site supervision and project management from demolition through drywall (approx. 6 months).

DEMOLITION, EXCAVATION & FOUNDATION SCOPE

Demolish and dispose of the existing dwelling, foundation and rear shed; clear vegetation in the work area.

Excavate for the basement (BFE 98.55) and frost walls at the garage, cold room and rear patio, including haul-away.

Form and pour strip and pad footings and poured concrete foundation walls per drawings.

Apply bituminous dampproofing and drainage mat; install weeping tile with clear stone to sump.

Backfill and rough grade to the AM Engineering grading plan.

Pour basement slab (3" on 6" granular, R10 perimeter insulation), garage slab, front porch and raised rear patio slabs.

Trench and install new water and sewer laterals to 1.0 m from the building face; install underground plumbing, sump and radon rough-in.

FRAMING & STRUCTURE SCOPE

Frame the house and garage: 2x10 floor systems, 2x6 exterior walls, interior partitions, engineered roof trusses and flat roof joists.

Supply and install structural steel beams and columns per drawings (7 beams, 5 columns).

Complete back framing, blocking and stair framing (basement stair left as framed).

ROOFING SCOPE

Supply and install asphalt shingles on the hip roof with underlayment, ice and water shield, flashings and roof vents.

Supply and install torch-on membrane on flat roofs over the garage, porch and patio, sloped to scuppers, with aluminum parapet capping.

Supply and install prefinished aluminum soffit, fascia, eavestrough and downspouts.

WINDOWS & EXTERIOR DOORS SCOPE

Supply and install vinyl double-pane low-E windows W1–W8 (14 units) per schedule, entry level, white.

Supply and install an 8'-0" vinyl patio sliding door with transom.

Supply and install insulated steel entry door with two sidelights, garage man door and gas-proofed garage-to-house door, with basic hardware.

Supply and install one 16'-0" x 8'-0" insulated steel garage door. Opener not included.

EXTERIOR CLADDING SCOPE

Supply and install brick and stone veneer on the main floor and stone columns, with ties and precast sills.

Supply and install stucco with R5 rigid insulation on the second floor and parapets.

Install sheathing membrane behind veneer and caulk all windows, doors and penetrations.

MECHANICAL & ELECTRICAL SCOPE

Rough-in plumbing for the powder room, main bath, ensuite, kitchen, laundry and two hose bibs. Basement 3-piece rough-in drains only.

Rough-in gas piping and venting for furnace, water heater and range.

Supply and install ductwork and HVAC rough-in; supply high-efficiency gas furnace, central A/C and HRV per HVAC design.

Install a new 200 A electrical service and rough-in all wiring and boxes to Ontario Electrical Safety Code, including basic basement lighting circuits.

Rough-in data/coax to main locations.

Mechanical and electrical finish (devices, fixture set, equipment startup) is not in this block; it is listed under Completion to Occupancy.

INSULATION & DRYWALL SCOPE

Insulate above-grade walls with R22 batt and 6 mil poly; install full-height insulation blanket on basement walls.

Blow in attic insulation; spray foam flat-roof areas over conditioned space and rim joists, to SB-12.

Complete a mid-construction air test before drywall.

Supply, hang, tape and finish drywall to Level 4 on the main and second floors and in the garage. Basement is not drywalled.

Prime and paint are not included.

CLOSEOUT SCOPE

Provide consumables, site cleanup at drywall turnover and demobilization.

Carry a construction contingency as a budget reserve; unused contingency is credited at closeout.

Block 2 Exclusions

Basement finishing (framing, drywall, flooring, bathroom fixtures).

All finishes and fixtures listed in Block 3, prime coat and paint, and mechanical/electrical finish and startup.

Driveway, walkways, sod, landscaping, fencing and final grading (see Block 3 / Completion option).

Garage door opener, window coverings, appliances, central vacuum, security and AV.

Rock removal, dewatering, engineered fill or shoring if soil conditions require it.

Water service upgrade beyond the existing service, and any City-required boulevard or road works.

Block 2 — Fixed Cost: $1,687,498

BLOCK 3 — FINISHED MATERIAL BUDGET (OPTIONAL, ENTRY LEVEL)

Required only if PalmView completes the home past drywall. Amounts are allowances at an entry-level finish. Final costs depend on selections; overages or credits are adjusted by change order, including PalmView's margin. Item-by-item allowances are in the attached Allowance Schedule.

Interior finish paint, 2 coats.

Hollow-core interior doors, lever hardware, MDF baseboard and casing, trim installation.

Vinyl plank / laminate flooring on main and second floor; ceramic tile in baths, laundry, entry and kitchen backsplash.

Finished main stair with oak/picket railing.

Pre-manufactured kitchen, island, pantry and laundry cabinets with entry-level countertops.

Bath vanities, plumbing fixtures, shower glass, mirrors and accessories.

Interior and exterior light fixtures.

Entry-level appliance package.

Exterior railing at the raised patio and front steps, precast steps, asphalt driveway and sod.

Block 3 — Finished Material Budget: $278,032

COMPLETION TO OCCUPANCY SCOPE (OPTIONAL, WITH BLOCK 3)

Complete plumbing, gas, HVAC and electrical finish: fixture set, devices, equipment startup.

Apply prime coat to main and second floor drywall.

Provide site supervision for the finishing phase (approx. 3 additional months) and waste bins.

Complete final grading and lot grading certificate, final air test, HVAC balancing, ESA and final building inspections and occupancy.

Provide professional final cleaning, deficiency completion and warranty service reserve.

Completion to Occupancy: $180,075

PRICE SUMMARY

| Block 1 — Owner Direct Costs (at cost) | $72,000 |
| --- | --- |
| Block 2 — Fixed Cost to Drywall | $1,687,498 |
| TOTAL TO DRYWALL (before HST) | $1,759,498 |
| HST 13% | $228,735 |
| TOTAL TO DRYWALL incl. HST | $1,988,233 |
| Optional: Block 3 — Finished Material Budget | $278,032 |
| Optional: Completion to Occupancy | $180,075 |
| TOTAL TURNKEY, ENTRY LEVEL (before HST) | $2,217,605 |
| HST 13% | $288,289 |
| TOTAL TURNKEY incl. HST | $2,505,894 |

PAYMENT SCHEDULE

Deposit — 10% on signing.

Beginning — 40% at start of construction.

Middle — 40% at framing / roof / windows complete.

End — 10% on completion of contracted scope.

GENERAL NOTES

Pricing is based on the drawings listed above. Changes to drawings, selections or site conditions requiring extras require a change order.

Framing lumber pricing is subject to a current lumber quote at time of contract.

Development charges, permit fees and utility fees are pass-through at cost and confirmed with the City and utilities.

All work to the Ontario Building Code, SB-12, Ontario Electrical Safety Code, CSA B149.1, O. Reg. 213/91 and Tarion Construction Performance Guidelines.

This quotation is valid until November 5, 2026.