## Summary
94 MARGARET AVE — PRICE TO DRYWALL
Rachel Milisic ¦ rmilisic@hotmail.com ¦ Stoney Creek (Hamilton), ON ¦ New 2-storey detached, entry level ¦ PalmView Contracting Inc. ¦ Oct 21, 2026
| ABOVE-GRADE AREA | PRICE TO DRYWALL | WITH HST | GROSS MARGIN | GROSS PROFIT | PRICE / SF
| 2930 | 1759497.875 | 1988232.5987 | 40% | 674999.15 | 600.5112
| Main 1,460 + Second 1,470 | before HST | 13% HST included | on PalmView price | to drywall | above grade
| HOUSE SIZE |  |  | PRICING INPUTS
| Main floor | 1460 |  | HST | 13%
| Second floor | 1470 |  | Contingency (on hard cost) | 5%
|  |  |  | TARGET GROSS MARGIN | 40%
| TOTAL ABOVE GRADE (finished) | 2930 |  | Equals markup on cost of | 66.67%
| Basement (unfinished, not in SF) | 1460 |  | Edit yellow cells; everything updates.
| Two-car garage | 548
DIVISION BREAKDOWN — FIXED PRICE TO DRYWALL
# | Division | Cost | Price | Gross Profit | Price / SF | % of Price
1 | Permits, Engineering & Soft Costs | 43800 | 73000 | 29200 | 24.9147 | 4.149%
2 | Site Supervision & General Conditions | 134750 | 224583.3333 | 89833.3333 | 76.6496 | 12.76%
3 | Demolition & Site Preparation | 35600 | 59333.3333 | 23733.3333 | 20.2503 | 3.372%
4 | Excavation, Backfill & Grading | 35270 | 58783.3333 | 23513.3333 | 20.0626 | 3.341%
5 | Footings, Foundation & Waterproofing | 93988 | 156646.6667 | 62658.6667 | 53.463 | 8.903%
6 | Concrete Slabs | 29904 | 49840 | 19936 | 17.0102 | 2.833%
7 | Framing & Structural Steel | 181384 | 302306.6667 | 120922.6667 | 103.1763 | 17.18%
8 | Roofing, Soffit, Fascia & Eaves | 43745 | 72908.3333 | 29163.3333 | 24.8834 | 4.144%
9 | Windows & Exterior Doors | 32984 | 54973.3333 | 21989.3333 | 18.7622 | 3.124%
10 | Exterior Cladding: Brick, Stone & Stucco | 162940 | 271566.6667 | 108626.6667 | 92.6849 | 15.43%
11 | Plumbing Rough-In | 26500 | 44166.6667 | 17666.6667 | 15.0739 | 2.51%
12 | HVAC & Gas Rough-In | 28500 | 47500 | 19000 | 16.2116 | 2.7%
13 | Electrical Rough-In & Service | 33350 | 55583.3333 | 22233.3333 | 18.9704 | 3.159%
14 | Insulation & Air Sealing | 22127.5 | 36879.1667 | 14751.6667 | 12.5867 | 2.096%
15 | Drywall (Level 4, unprimed) | 48692 | 81153.3333 | 32461.3333 | 27.6974 | 4.612%
16 | Site Cleanup & Closeout | 10750 | 17916.6667 | 7166.6667 | 6.1149 | 1.018%
17 | Construction Contingency (5% reserve) | 48214.225 | 80357.0417 | 32142.8167 | 27.4256 | 4.567%
| PALMVIEW FIXED PRICE (40% margin) | 1012498.725 | 1687497.875 | 674999.15 | 575.9378 | 95.91%
| Municipal & Utility Fees — permit, DCs, utilities (at cost, no margin) | 72000 | 72000 | 0 | 24.5734 | 4.092%
| TOTAL TO DRYWALL (before HST) | 1084498.725 | 1759497.875 | 674999.15 | 600.5112 | 100%
| HST 13% |  | 228734.7238
| TOTAL INCLUDING HST |  | 1988232.5987
MARGIN CHECK — PALMVIEW SCOPE (EXCLUDES PASS-THROUGH FEES)
| PalmView cost (incl. contingency) | 1012498.725 |  | 40% margin means 40 cents of every dollar the client pays
| PalmView price | 1687497.875 |  | is gross profit. On cost, that is a 66.7% markup.
| Gross profit | 674999.15 |  | PalmView's standard 35% markup would equal a 25.9% margin.
| Gross margin (profit ÷ price) | 40% |  | Fees passed through at cost carry no margin.
| Markup (profit ÷ cost) | 66.67%
INCLUDED TO DRYWALL |  |  |  | NOT INCLUDED
✓ Demolition of existing house and site prep |  |  |  | ✕ Prime coat and paint
✓ Excavation, foundation, waterproofing, slabs |  |  |  | ✕ Mechanical and electrical finish and startup
✓ Framing, steel, trusses, roofing |  |  |  | ✕ All interior finishes and fixtures
✓ Vinyl double-pane windows, steel doors, garage door |  |  |  | ✕ Basement finishing (left unfinished)
✓ Brick, stone and stucco as drawn |  |  |  | ✕ Driveway, landscaping, final grading
✓ Plumbing, gas, HVAC and electrical ROUGH-IN only |  |  |  | ✕ Garage door opener, appliances
✓ Furnace, A/C, HRV supply; 200 A service |  |  |  | ✕ Rock, dewatering, shoring if required
✓ Insulation, air test, Level 4 drywall (unprimed) |  |  |  | ✕ HST (shown separately)
Confirm before issue: lumber quote, Hamilton development charge credit, foundation wall thickness, abatement after DSS, window count.

## Division Detail
DIVISION DETAIL — FIXED PRICE TO DRYWALL
Every line item behind the Summary. Blue = quantities and unit costs from the PalmView Cost Index; price = cost ÷ (1 − margin).
Code | Cost Item | Scope Description | Qty | Unit | Unit Cost | Cost | Price
PERMITS, ENGINEERING & SOFT COSTS
1.002 | City Permit Package | City permit package: zoning review, application forms and submission to City of Hamilton. | 1 | Lump Sum | 15000 | 15000 | 25000
1.029 | Permit Coordination Fee | Permit coordination with City, designer (Bobicon) and AM Engineering through issuance. | 1 | Lump Sum | 3000 | 3000 | 5000
1.007 | Engineering (Structural, Mechanical & Heat Loss) | Engineering: structural (steel beams, lintels), HVAC design and heat loss / SB-12 EEDS. | 1 | Lump Sum | 7000 | 7000 | 11666.6667
1.070 | Truss Layout Drawings | Truss layout drawings for hip roof and girder trusses. | 1 | Lump Sum | 1500 | 1500 | 2500
1.030 | Surveyor Stakeout, Footing Pins & Wall Pins | Surveyor stakeout, footing pins and wall pins. | 1 | Lump Sum | 2200 | 2200 | 3666.6667
1.031 | As-Built Survey / Survey Revisions | As-built / foundation location survey. | 1 | Lump Sum | 1800 | 1800 | 3000
1.020 | Site Field Reviews by Engineer | AM Engineering site reviews: servicing inspection and lot grading. | 2 | Each | 1800 | 3600 | 6000
1.067 | Hazardous Substance Report | Designated substance survey of existing house before demolition (O. Reg. 278/05). | 1 | Lump Sum | 1200 | 1200 | 2000
1.021 | Tarion Warranty Enrollment | Tarion new home warranty enrolment. | 1 | Lump Sum | 8500 | 8500 | 14166.6667
| Subtotal — Permits, Engineering & Soft Costs |  |  |  |  | 43800 | 73000
SITE SUPERVISION & GENERAL CONDITIONS
1.036 | Tree Protection | Tree protection hoarding at City boulevard tree per City of Hamilton requirements. | 1 | Lump Sum | 4500 | 4500 | 7500
1.040 | Site Supervision & Project Management (Blended Monthly) | Site supervision and project management, 6 months demo through drywall. | 6 | Months | 12000 | 72000 | 120000
1.042 | Temporary Hoarding & Safety Fences | Temporary construction fence, front and sides. | 160 | Linear Feet | 45 | 7200 | 12000
1.043 | Temporary Toilet | Temporary toilet, 6 months. | 6 | Months | 250 | 1500 | 2500
1.044 | Temporary Hydro | Temporary hydro service. | 1 | Lump Sum | 3500 | 3500 | 5833.3333
1.045 | Temporary Water | Temporary water. | 1 | Lump Sum | 2800 | 2800 | 4666.6667
1.046 | Temporary Heating (Winter) | Temporary heat, winter months (if schedule falls in winter). | 3 | Months | 2200 | 6600 | 11000
1.047 | Crane Service (incl. Operator & Rigging) | Crane with operator to set roof trusses, 1 day. | 1 | Days | 2800 | 2800 | 4666.6667
1.050 | Scaffold Rental | Scaffold rental for masonry and stucco, 4 months. | 4 | Months | 1500 | 6000 | 10000
1.051 | Waste Disposal / Garbage Bins | Waste bins and disposal, 6 months. | 6 | Months | 1800 | 10800 | 18000
1.052 | Miscellaneous Supplies & Materials | Miscellaneous supplies and materials. | 1 | Lump Sum | 8000 | 8000 | 13333.3333
1.053 | Safety Supplies | Safety supplies, fall protection, first aid. | 1 | Lump Sum | 3500 | 3500 | 5833.3333
1.054 | Site Signage | Site signage. | 1 | Each | 450 | 450 | 750
1.056 | Sidewalk / Road Protection | Sidewalk and road protection; existing driveway kept for access during construction. | 1 | Lump Sum | 3000 | 3000 | 5000
1.063 | Insurance | Builder's risk insurance. | 1 | Lump Sum | 1200 | 1200 | 2000
1.069 | Line Protection / Utility Locates | Utility locates. | 1 | Lump Sum | 900 | 900 | 1500
| Subtotal — Site Supervision & General Conditions |  |  |  |  | 134750 | 224583.3333
DEMOLITION & SITE PREPARATION
1.068 | Environmental Abatement | Provisional environmental abatement allowance for existing house (asbestos/vermiculite). | 1 | Lump Sum | 8000 | 8000 | 13333.3333
2.001 | House Demolition | Demolish existing 1-storey dwelling incl. basement, foundations and rear shed; dispose. | 1300 | Square Foot | 12 | 15600 | 26000
2.003 | Site Clearing | Site clearing of shrubs, vegetation and stumps within the building and work area. | 1 | Lump Sum | 12000 | 12000 | 20000
| Subtotal — Demolition & Site Preparation |  |  |  |  | 35600 | 59333.3333
EXCAVATION, BACKFILL & GRADING
2.019 | Excavation & Ground works | Excavate basement (1,460 SF, BFE 98.55) plus overdig and frost wall trenches; incl. haul-away of excess per index scope. | 600 | Cubic Yard | 22 | 13200 | 22000
2.070 | Backfill | Backfill foundation walls and frost walls. | 190 | Cubic Yard | 28 | 5320 | 8866.6667
2.073 | Rough Grading | Rough grading around building per AM Engineering grading plan. | 2500 | Square Foot | 5 | 12500 | 20833.3333
2.071 | Service Trenching | Service trenching for new water and sewer laterals to 1.0 m from building face. | 50 | Linear Feet | 85 | 4250 | 7083.3333
| Subtotal — Excavation, Backfill & Grading |  |  |  |  | 35270 | 58783.3333
FOOTINGS, FOUNDATION & WATERPROOFING
2.046 | Footings (Forming, Rebar & Concrete) | Strip footings at basement, garage and patio frost walls plus pad footings, all-in. | 314 | Linear Feet | 70 | 21980 | 36633.3333
2.080 | Foundation Walls - Poured In Place (8" formed, 3-bar) | Basement foundation walls incl. cold room, approx. 8'-10" high, all-in. Drawings show 10"/12" walls; confirm thickness. | 181 | Linear Feet | 150 | 27150 | 45250
2.080 | Foundation Walls - Poured In Place (8" formed, 3-bar) | Garage and rear patio frost walls (unexcavated areas), all-in. | 113 | Linear Feet | 150 | 16950 | 28250
2.051 | Waterproofing | Bituminous dampproofing and drainage mat on basement walls below grade. | 1360 | Square Foot | 12 | 16320 | 27200
2.053 | Weeping Tile | Weeping tile at basement footing perimeter to sump. | 181 | Linear Feet | 28 | 5068 | 8446.6667
2.058 | Perimeter Drainage 3/4" Crush | 3/4" clear stone cover over weeping tile. | 90 | Ton | 48 | 4320 | 7200
3.105 | Concrete Pump (hardscape) | Concrete pumping, all foundation and slab pours (approx. 100 CY). | 100 | Cubic Yard | 22 | 2200 | 3666.6667
| Subtotal — Footings, Foundation & Waterproofing |  |  |  |  | 93988 | 156646.6667
CONCRETE SLABS
2.054 | Basement Slab | Basement slab: 3" 25 MPa on 6" granular, R10 perimeter insulation per slab detail. | 1460 | Square Foot | 12 | 17520 | 29200
2.054 | Basement Slab | Garage slab on compacted granular. | 548 | Square Foot | 12 | 6576 | 10960
2.056 | Porch Slabs | Front porch (60 SF) and raised rear covered patio (204 SF) slabs. | 264 | Square Foot | 22 | 5808 | 9680
| Subtotal — Concrete Slabs |  |  |  |  | 29904 | 49840
FRAMING & STRUCTURAL STEEL
3.002 | Framing Materials | Framing materials: house 2,930 SF + garage 548 SF, incl. floors, walls, roof trusses, flat roofs, sheathing. LIVE LUMBER QUOTE REQUIRED. | 3478 | Square Foot | 20 | 69560 | 115933.3333
3.006 | Framing Labour | Framing labour, same area. | 3478 | Square Foot | 18 | 62604 | 104340
3.133 | Back Framing - Whole-House Basis (budget stage) | Back framing, whole-house budget basis (blocking, bulkheads, stair framing). | 2930 | Square Foot | 4 | 11720 | 19533.3333
3.009 | Steel Beams | Steel beams: W10x22 x2 (basement), W8x28, W8x31/W10x22, W8x18 x2, W10x26 (garage). | 7 | Each | 4500 | 31500 | 52500
3.010 | Steel Posts | Steel posts / columns with base plates. | 5 | Each | 1200 | 6000 | 10000
| Subtotal — Framing & Structural Steel |  |  |  |  | 181384 | 302306.6667
ROOFING, SOFFIT, FASCIA & EAVES
3.014 | Roofing material & labour (Shingle) | Asphalt shingle hip roof incl. underlayment, ice & water, flashings and roof vents (5/12, approx. 1,850 SF). | 1850 | Square Foot | 8 | 14800 | 24666.6667
3.015 | Torch on install and supply (Flat Roof) | Torch-on flat roof membrane over garage, front porch, rear patio and front roof sections, sloped 2% to scuppers. | 950 | Square Foot | 12 | 11400 | 19000
3.032 | Flashing and aluminum capping | Aluminum parapet capping and flashing at flat roofs. | 165 | Linear Feet | 45 | 7425 | 12375
3.069 | Soffits | Prefinished aluminum soffit. | 220 | Linear Feet | 16 | 3520 | 5866.6667
3.070 | Fascia | Prefinished aluminum fascia. | 220 | Linear Feet | 14 | 3080 | 5133.3333
3.071 | Eavestroughs & Downspouts | Eavestrough and downspouts. | 220 | Linear Feet | 16 | 3520 | 5866.6667
| Subtotal — Roofing, Soffit, Fascia & Eaves |  |  |  |  | 43745 | 72908.3333
WINDOWS & EXTERIOR DOORS
3.019 | Windows (Basic vinyl) | Vinyl double-pane low-E windows W1-W8 (14 units, approx. 430 SF), supply and install. | 430 | Square Foot | 42 | 18060 | 30100
3.019 | Windows (Basic vinyl) | D3 vinyl patio sliding door 8'-0" x 9'-0" with transom, supply and install. | 72 | Square Foot | 42 | 3024 | 5040
3.027 | Exterior Doors (Basic Steel) | Insulated steel exterior doors: D1 entry (with 2 sidelights), D2 garage man door, garage-to-house door (self-closing, gas-proofed). | 3 | Each | 1800 | 5400 | 9000
3.028 | Exterior Door Installation | Exterior door installation. | 3 | Each | 650 | 1950 | 3250
3.029 | Exterior Door Hardware | Exterior door hardware (basic lever / entry handleset, deadbolt). | 3 | Each | 350 | 1050 | 1750
3.030 | Garage Doors (standard size) | D4 16'-0" x 8'-0" insulated steel garage door (opener not included). | 1 | Each | 3500 | 3500 | 5833.3333
| Subtotal — Windows & Exterior Doors |  |  |  |  | 32984 | 54973.3333
EXTERIOR CLADDING: BRICK, STONE & STUCCO
3.073 | Exterior Masonry material | Brick and stone veneer, main floor and 4 stone columns, incl. ties, precast sills, brick ledge (supply and install). | 2200 | Square Foot | 45 | 99000 | 165000
3.078 | Stucco | Stucco veneer w/ R5 rigid, 2nd floor and parapets (supply and install). | 1850 | Square Foot | 28 | 51800 | 86333.3333
3.061 | House Wrap | Sheathing membrane (Tyvek) behind brick/stone veneer. | 2200 | Square Foot | 3.5 | 7700 | 12833.3333
3.072 | Exterior Caulking | Exterior caulking at windows, doors and penetrations. | 370 | Linear Feet | 12 | 4440 | 7400
| Subtotal — Exterior Cladding: Brick, Stone & Stucco |  |  |  |  | 162940 | 271566.6667
PLUMBING ROUGH-IN
3.001 | Plumbing - Underground | Underground plumbing: basement drains, sump, floor drain, 3-pc rough-in drains, radon rough-in, laterals. | 100 | Linear Feet | 85 | 8500 | 14166.6667
3.047 | Rough-In Plumbing | Plumbing rough-in: powder room, main bath, ensuite, kitchen, laundry, 2 hose bibs; basement 3-pc rough-in only. | 1 | Lump Sum | 18000 | 18000 | 30000
| Subtotal — Plumbing Rough-In |  |  |  |  | 26500 | 44166.6667
HVAC & GAS ROUGH-IN
3.048 | Rough-In Gas & Venting | Gas rough-in and venting: furnace, water heater, range. | 1 | Lump Sum | 6500 | 6500 | 10833.3333
3.049 | Rough-In HVAC | HVAC: high-efficiency gas furnace, central A/C, HRV, ductwork and controls. | 1 | Lump Sum | 22000 | 22000 | 36666.6667
| Subtotal — HVAC & Gas Rough-In |  |  |  |  | 28500 | 47500
ELECTRICAL ROUGH-IN & SERVICE
3.046 | Electrical - Underground | Electrical underground service trench from street. | 50 | Linear Feet | 65 | 3250 | 5416.6667
3.050 | Electrical Service (200 Amp if required) | New 200 A electrical service and panel. | 1 | Lump Sum | 8500 | 8500 | 14166.6667
3.051 | Electrical Rough-In | Electrical rough-in: devices, pot lights, smoke/CO, appliance circuits; basic code lighting/outlets in basement. | 1 | Lump Sum | 18000 | 18000 | 30000
3.042 | Low voltage rough wire | Low-voltage rough wire: data/coax to main locations. | 200 | Linear Feet | 18 | 3600 | 6000
| Subtotal — Electrical Rough-In & Service |  |  |  |  | 33350 | 55583.3333
INSULATION & AIR SEALING
3.054 | Batt Insulation | R22 batt + 6 mil poly at above-grade walls (3,060 SF) and full-height basement wall blanket (1,450 SF). | 4510 | Square Foot | 2 | 9020 | 15033.3333
3.125 | Insulation (Blown-in) | Blown-in attic insulation to SB-12 value. | 1470 | Square Foot | 2.25 | 3307.5 | 5512.5
3.053 | Spray-foam | Closed-cell spray foam at flat roof over office/entry and rim joists. | 500 | Square Foot | 14 | 7000 | 11666.6667
3.056 | Air Testing (prior to drywall) | Mid-construction air test before drywall (SB-12 performance path). | 1 | Lump Sum | 2800 | 2800 | 4666.6667
| Subtotal — Insulation & Air Sealing |  |  |  |  | 22127.5 | 36879.1667
DRYWALL (LEVEL 4, UNPRIMED)
4.001 | Drywall (1/2") | Drywall, Level 4 finish: main and 2nd floor + garage (rate on floor area). Basement NOT drywalled. No prime. | 3478 | Square Foot | 14 | 48692 | 81153.3333
| Subtotal — Drywall (Level 4, unprimed) |  |  |  |  | 48692 | 81153.3333
SITE CLEANUP & CLOSEOUT
5.001 | Consumables (Miscellaneous construction materials) | Consumables. | 1 | Lump Sum | 4500 | 4500 | 7500
5.013 | Final Site Cleanup | Site cleanup at drywall turnover. | 1 | Lump Sum | 5500 | 5500 | 9166.6667
5.020 | Demobilization | Demobilization. | 1 | Lump Sum | 500 | 500 | 833.3333
5.021 | Sign Removal | Sign removal. | 1 | Lump Sum | 250 | 250 | 416.6667
| Subtotal — Site Cleanup & Closeout |  |  |  |  | 10750 | 17916.6667
Code | Cost Item | Scope Description | Qty | Unit | Unit Cost | Cost | Price
MUNICIPAL & UTILITY FEES (PASS-THROUGH)
1.016 | Building Permit Fees | Building permit fees, City of Hamilton (new SFD + grading review). Pass-through at cost. | 1 | Lump Sum | 12000 | 12000 | 12000
1.034 | Development Charges | Development charges, City of Hamilton. Knock-down-rebuild default; demolition credit to be confirmed. | 1 | Lump Sum | 45000 | 45000 | 45000
1.035 | Utility Connection Fees | Utility connection fees bundle: water/sewer permits, gas and hydro service fees. Pass-through at cost. | 1 | Lump Sum | 15000 | 15000 | 15000
| Subtotal — Municipal & Utility Fees (pass-through) |  |  |  |  | 72000 | 72000

## Turnkey Option
TURNKEY OPTION — ENTRY-LEVEL FINISHES TO OCCUPANCY
Not included in the price to drywall. Shown so the client can see the cost to finish with PalmView.
OPTIONAL — COST TO FINISH WITH PALMVIEW (ENTRY LEVEL)
| Division |  |  |  |  | Cost | Price
| Mechanical & Electrical Finish |  |  |  |  | 19000 | 31666.6667
| Prime & Finish Paint |  |  |  |  | 14650 | 24416.6667
| Interior Doors, Trim & Hardware |  |  |  |  | 35590 | 59316.6667
| Flooring & Tile |  |  |  |  | 34354.5 | 57257.5
| Stairs & Railings |  |  |  |  | 9080 | 15133.3333
| Cabinets & Countertops |  |  |  |  | 21375 | 35625
| Fixtures, Lighting, Glass & Appliances |  |  |  |  | 30330 | 50550
| Exterior Railings, Steps, Driveway & Sod |  |  |  |  | 25835 | 43058.3333
| Finishing Supervision, Inspections & Closeout |  |  |  |  | 84650 | 141083.3333
| Total optional finishing |  |  |  |  | 274864.5 | 458107.5
| Price to drywall (from Summary) |  |  |  |  | 1084498.725 | 1759497.875
| TURNKEY TOTAL, ENTRY LEVEL (before HST) |  |  |  |  | 1359363.225 | 2217605.375
| Turnkey price per SF above grade | [5 empty] | 756.8619
Code | Cost Item | Scope Description | Qty | Unit | Unit Cost | Cost | Price
MECHANICAL & ELECTRICAL FINISH
3.037 | Plumbing - Finish & Fixture Set | Plumbing finish and fixture set (fixtures by allowance). | 1 | Lump Sum | 4000 | 4000 | 6666.6667
3.035 | Gas - Finish & Appliance Connections | Gas finish and appliance connections. | 1 | Lump Sum | 2000 | 2000 | 3333.3333
3.033 | HVAC - Finish, Equipment Set & Startup | HVAC finish, equipment set and startup. | 1 | Lump Sum | 6000 | 6000 | 10000
3.040 | Electrical - Finish, Devices & Fixture Hookup | Electrical finish, devices and fixture hookup (fixtures by allowance). | 1 | Lump Sum | 7000 | 7000 | 11666.6667
| Subtotal — Mechanical & Electrical Finish |  |  |  |  | 19000 | 31666.6667
PRIME & FINISH PAINT
4.002 | Interior Painting - Prime Coat | Interior prime coat, main and 2nd floor. | 2930 | Square Foot | 1.5 | 4395 | 7325
4.070 | Interior Painting - Finish Coats | Interior finish paint, 2 coats, builder white, main and 2nd floor. | 2930 | Square Foot | 3.5 | 10255 | 17091.6667
| Subtotal — Prime & Finish Paint |  |  |  |  | 14650 | 24416.6667
INTERIOR DOORS, TRIM & HARDWARE
4.004 | Interior Doors | Interior doors, hollow-core moulded slab, pre-hung, installed. | 22 | Each | 650 | 14300 | 23833.3333
4.006 | Interior Door Hardware | Interior door hardware, entry-level levers. | 22 | Each | 45 | 990 | 1650
4.008 | Molding Materials | MDF baseboard and casing, paint grade. | 2100 | Linear Feet | 4 | 8400 | 14000
4.010 | Finish Carpentry (Trim Moldings and doors labour) | Finish carpentry labour, trim install. | 140 | Hours | 85 | 11900 | 19833.3333
| Subtotal — Interior Doors, Trim & Hardware |  |  |  |  | 35590 | 59316.6667
FLOORING & TILE
4.052 | Flooring Allowance (if applicable) | Flooring allowance: vinyl plank / laminate, main and 2nd floor, supply and install. | 2450 | Square Foot | 8 | 19600 | 32666.6667
4.053 | Tile Allowance (if applicable) | Tile supply allowance: bath/laundry/entry floors, shower and tub walls, backsplash. | 505 | Square Foot | 6 | 3030 | 5050
4.014 | Tile Installation Labour (general floor & wall) | Tile install labour, floors. | 335 | Square Foot | 15 | 5025 | 8375
4.013 | Tile Setting Materials (thinset, membrane, backer) | Tile setting materials, floors. | 335 | Square Foot | 8.5 | 2847.5 | 4745.8333
4.061 | Tile Shower Wall - Install (labour + setting materials) | Tile install, shower and tub walls (labour + setting materials). | 140 | Square Foot | 18 | 2520 | 4200
4.060 | Tile Shower Floor - Install (labour + setting materials) | Tile install, ensuite shower floor. | 16 | Square Foot | 12 | 192 | 320
4.062 | Tile Backsplash - Install (labour + setting materials) | Tile install, kitchen backsplash. | 30 | Square Foot | 38 | 1140 | 1900
| Subtotal — Flooring & Tile |  |  |  |  | 34354.5 | 57257.5
STAIRS & RAILINGS
4.030 | Custom Stairs | Main-to-2nd floor stair finish (basement stair left as framed). | 1 | Lump Sum | 5000 | 5000 | 8333.3333
4.029 | Interior Railing | Interior railing, stair and 2nd floor landing, entry-level oak/picket. | 34 | Linear Feet | 120 | 4080 | 6800
| Subtotal — Stairs & Railings |  |  |  |  | 9080 | 15133.3333
CABINETS & COUNTERTOPS
4.032 | Cabinets - Pre-manufactured | Pre-manufactured cabinets: kitchen, island, pantry, laundry. | 40 | Linear Feet | 280 | 11200 | 18666.6667
4.034 | Cabinet install | Cabinet install. | 40 | Linear Feet | 85 | 3400 | 5666.6667
4.054 | Cabinet Hardware Allowance (if applicable) | Cabinet hardware allowance. | 1 | Lump Sum | 600 | 600 | 1000
4.035 | Countertops | Countertops, entry-level quartz/laminate, kitchen and island. | 95 | Square Foot | 65 | 6175 | 10291.6667
| Subtotal — Cabinets & Countertops |  |  |  |  | 21375 | 35625
FIXTURES, LIGHTING, GLASS & APPLIANCES
4.064 | Bath Vanities | Bath vanities with tops: powder, main bath, ensuite. | 3 | Each | 1200 | 3600 | 6000
4.050 | Plumbing Fixture Allowance | Plumbing fixture allowance (3 toilets, faucets, tub, freestanding tub, shower valve, kitchen sink, laundry tub). | 1 | Lump Sum | 9000 | 9000 | 15000
4.051 | Lighting Fixture Allowance | Interior lighting fixture allowance. | 1 | Lump Sum | 4500 | 4500 | 7500
3.091 | Exterior Lighting | Exterior light fixture allowance. | 6 | Each | 150 | 900 | 1500
4.058 | Shower Glass | Ensuite shower glass. | 1 | Each | 1500 | 1500 | 2500
4.069 | Mirrors | Bathroom mirrors. | 3 | Each | 250 | 750 | 1250
4.040 | Hardware & Accessories fixtures | Bath accessories (towel bars, TP holders). | 9 | Each | 120 | 1080 | 1800
4.037 | Appliance Package | Appliance package allowance, entry level (fridge, range, DW, hood, W/D). | 1 | Lump Sum | 9000 | 9000 | 15000
| Subtotal — Fixtures, Lighting, Glass & Appliances |  |  |  |  | 30330 | 50550
EXTERIOR RAILINGS, STEPS, DRIVEWAY & SOD
3.092 | Exterior Railing | Exterior aluminum vista railing at raised patio and front steps. | 37 | Linear Feet | 85 | 3145 | 5241.6667
3.108 | Masonry Supply | Precast steps, front porch and rear patio (supply). | 40 | Square Foot | 65 | 2600 | 4333.3333
3.109 | Masonry Labour | Precast steps, install. | 40 | Square Foot | 45 | 1800 | 3000
3.110 | Asphalt areas | New asphalt driveway (approx. 24'-6" x 36'). | 880 | Square Foot | 8 | 7040 | 11733.3333
3.120 | Grass roll Supply | Sod supply, disturbed areas. | 5000 | Square Foot | 1.25 | 6250 | 10416.6667
3.121 | Grass roll Labour | Sod install. | 5000 | Square Foot | 1 | 5000 | 8333.3333
| Subtotal — Exterior Railings, Steps, Driveway & Sod |  |  |  |  | 25835 | 43058.3333
FINISHING SUPERVISION, INSPECTIONS & CLOSEOUT
1.040 | Site Supervision & Project Management (Blended Monthly) | Site supervision and PM, finishing phase, 3 additional months. | 3 | Months | 12000 | 36000 | 60000
1.051 | Waste Disposal / Garbage Bins | Waste bins, finishing phase. | 2 | Months | 1800 | 3600 | 6000
5.005 | Final Grade | Final grading and lot grading certificate. | 2500 | Square Foot | 4.5 | 11250 | 18750
3.060 | Final Air test | Final air test. | 1 | Lump Sum | 1800 | 1800 | 3000
5.006 | HVAC Balancing | HVAC balancing. | 1 | Lump Sum | 1800 | 1800 | 3000
5.007 | Electrical Inspection (ESA) | ESA final inspection. | 1 | Lump Sum | 1200 | 1200 | 2000
5.008 | Final Building Inspections | Final building inspections. | 1 | Lump Sum | 2500 | 2500 | 4166.6667
5.009 | Occupancy Requirements | Occupancy requirements. | 1 | Lump Sum | 1500 | 1500 | 2500
5.010 | Professional Final Cleaning | Professional final cleaning. | 1 | Lump Sum | 4500 | 4500 | 7500
5.012 | Deficiency Completion / Touch-Ups | Deficiency completion and touch-ups. | 1 | Lump Sum | 8500 | 8500 | 14166.6667
5.014 | Warranty Service Allowance | Warranty service reserve. | 1 | Lump Sum | 12000 | 12000 | 20000
| Subtotal — Finishing Supervision, Inspections & Closeout |  |  |  |  | 84650 | 141083.3333

## Schedule
APPROXIMATE SCHEDULE
Week 1 = construction start after permit. Change the yellow start date and every date updates.
Construction start (Week 1, Monday) |  |  | 2027-01-11
[7 empty] | Nov 16 |  |  |  | Dec 14 |  |  |  | Jan 11 |  |  |  | Feb 8 |  |  |  | Mar 8 |  |  |  | Apr 5 |  |  |  | May 3 |  |  |  | May 31 |  |  |  | Jun 28 |  |  |  | Jul 26 |  |  |  | Aug 23 |  |  |  | Sep 20
Phase | Trade | Start Wk | Weeks | End Wk | Start | Finish | -7 | -6 | -5 | -4 | -3 | -2 | -1 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
PRE-CONSTRUCTION
Permit issuance, utility disconnects, hazardous survey | Owner / PalmView | -7 | 8 | 0 | 2026-11-16 | 2027-01-08
FIXED SCOPE — TO DRYWALL
Site setup, fencing, tree protection | PalmView | 1 | 1 | 1 | 2027-01-11 | 2027-01-15
Abatement (if required) | Abatement | 1 | 1 | 1 | 2027-01-11 | 2027-01-15
Demolition & site clearing | Demolition | 2 | 2 | 3 | 2027-01-18 | 2027-01-29
Stakeout & excavation | Survey / Excavation | 4 | 1 | 4 | 2027-02-01 | 2027-02-05
Footings | Forming | 5 | 1 | 5 | 2027-02-08 | 2027-02-12
Foundation walls | Forming | 6 | 2 | 7 | 2027-02-15 | 2027-02-26
Dampproofing, weeping tile, underground services | Waterproof / Plumber | 8 | 1 | 8 | 2027-03-01 | 2027-03-05
Backfill & rough grade | Excavation | 9 | 1 | 9 | 2027-03-08 | 2027-03-12
Framing & structural steel | Framer / Steel | 10 | 5 | 14 | 2027-03-15 | 2027-04-16
Roof trusses (crane) & sheathing | Framer | 14 | 1 | 14 | 2027-04-12 | 2027-04-16
Roofing: shingles & flat roofs | Roofer | 15 | 2 | 16 | 2027-04-19 | 2027-04-30
Windows & exterior doors | Windows | 15 | 2 | 16 | 2027-04-19 | 2027-04-30
Plumbing, gas, HVAC & electrical rough-ins | Mech / Elec | 16 | 4 | 19 | 2027-04-26 | 2027-05-21
Basement & garage slabs | Concrete | 17 | 1 | 17 | 2027-05-03 | 2027-05-07
Brick, stone & stucco | Mason / Stucco | 17 | 6 | 22 | 2027-05-03 | 2027-06-11
Framing & rough-in inspections | City of Hamilton | 20 | 1 | 20 | 2027-05-24 | 2027-05-28
Insulation, spray foam, air test | Insulator | 21 | 2 | 22 | 2027-05-31 | 2027-06-11
Soffit, fascia, eavestrough | Exterior | 23 | 1 | 23 | 2027-06-14 | 2027-06-18
Drywall: board, tape, finish (Level 4) | Drywaller | 23 | 4 | 26 | 2027-06-14 | 2027-07-09
Drywall complete — fixed scope handover | PalmView | 27 | 1 | 27 | 2027-07-12 | 2027-07-16
OPTIONAL — FINISH TO OCCUPANCY
Prime, trim, doors, stairs & railings | Finish carpentry | 28 | 3 | 30 | 2027-07-19 | 2027-08-06
Cabinets & countertops | Cabinets / Counters | 28 | 4 | 31 | 2027-07-19 | 2027-08-13
Flooring & tile | Flooring / Tile | 30 | 4 | 33 | 2027-08-02 | 2027-08-27
Finish paint | Painter | 33 | 2 | 34 | 2027-08-23 | 2027-09-03
Mechanical & electrical finish, fixtures | Mech / Elec | 34 | 2 | 35 | 2027-08-30 | 2027-09-10
Final grade, driveway, sod | Landscape / Paving | 34 | 3 | 36 | 2027-08-30 | 2027-09-17
Final clean, inspections, occupancy | PalmView / City | 37 | 2 | 38 | 2027-09-20 | 2027-10-01
Deficiencies & handover | PalmView | 39 | 1 | 39 | 2027-10-04 | 2027-10-08
KEY DATES
Construction start |  |  |  |  | 2027-01-11
Foundation complete |  |  |  |  | 2027-03-12
Closed in: framed, roofed, windows |  |  |  |  | 2027-04-30
DRYWALL COMPLETE — FIXED SCOPE DONE (~6 months) |  |  |  |  | 2027-07-16
Occupancy, if finishing is added (~9 months) |  |  |  |  | 2027-10-08